## 1000 Interfaces
# | Theme | Unforeseen circumstance | Systems impacted | Foundational relationship | Building category | Project type
1 | 1. Ground, Earthworks & Foundations | Rock found at footing depth | Footings ↔ Ground | Footings must hand load to ground of known capacity. | All | New build/Extension
2 | 1. Ground, Earthworks & Foundations | Groundwater floods the excavation | Basement walls ↔ Hydrology | Below-grade structure must resist water pressure it was never sized for. | Res/Com | New build/Extension
3 | 1. Ground, Earthworks & Foundations | Contaminated soil discovered | Earthworks ↔ Site environment | Excavation depth is set by structure but disposal rules are set by the soil. | All | New build/Extension
4 | 1. Ground, Earthworks & Foundations | Unmapped utility in the footing line | Underground services ↔ Footings | Structure and buried services compete for the same ground. | All | All
5 | 1. Ground, Earthworks & Foundations | Reactive clay swells after rain | Slab ↔ Soil | A slab rides on soil moisture movement. | Res/Com | New build/Extension
6 | 1. Ground, Earthworks & Foundations | Neighbour's footing undermined | Excavation/shoring ↔ Adjoining structure | Removing lateral support transfers risk to the neighbour. | All | New build/Extension
7 | 1. Ground, Earthworks & Foundations | Soft spot under the slab | Slab ↔ Subgrade | A slab needs uniform support to span as designed. | All | New build/Extension
8 | 1. Ground, Earthworks & Foundations | Tree roots at footing line | Footings ↔ Landscape | Living roots change soil moisture and bearing. | Res | All
9 | 1. Ground, Earthworks & Foundations | Pile hits an old buried obstruction | Piles ↔ Ground | Piles assume a continuous known ground profile. | Com/Ind | New build
10 | 1. Ground, Earthworks & Foundations | Heavy rain saturates the subgrade | Temporary drainage ↔ Subgrade | Wet soil loses strength so drainage protects bearing. | All | New build/Extension
11 | 1. Ground, Earthworks & Foundations | Dewatering settles neighbouring buildings | Dewatering ↔ Adjacent foundations | Lowering the water table changes soil support nearby. | Com | New build
12 | 1. Ground, Earthworks & Foundations | Old tanks or slabs found underground | Demolition legacy ↔ New footings | New structure needs clean stable ground. | All | New build/Extension
13 | 1. Ground, Earthworks & Foundations | Geotech report did not match actual ground | Foundation design ↔ Site investigation | Footing design is only as good as the ground data behind it. | All | New build/Extension
14 | 1. Ground, Earthworks & Foundations | Fill material found under the building pad | Slab/footings ↔ Uncontrolled fill | Footings need natural or engineered ground not tipped waste. | Res/Ind | New build/Extension
15 | 1. Ground, Earthworks & Foundations | Acid sulfate soil exposed by excavation | Earthworks ↔ Environmental controls | Disturbed soil oxidises and attacks concrete and waterways. | All | New build
16 | 1. Ground, Earthworks & Foundations | Excavated spoil volume far above estimate | Earthworks ↔ Haulage logistics | Cut volume drives truck movements and program. | Com/Ind | New build
17 | 1. Ground, Earthworks & Foundations | Shoring wall deflects more than predicted | Temporary shoring ↔ Adjacent structures | Retention must hold movement within neighbour tolerances. | Com | New build
18 | 1. Ground, Earthworks & Foundations | Ground anchors clash with neighbour's basement | Anchors ↔ Adjoining property | Retention systems extend beyond the site boundary. | Com | New build
19 | 1. Ground, Earthworks & Foundations | Anchor fails proof load test | Ground anchors ↔ Soil strength | Anchor capacity depends on soil friction not assumption. | Com | New build
20 | 1. Ground, Earthworks & Foundations | Soldier pile misaligned at excavation | Retention ↔ Basement wall line | Retention position sets the usable basement footprint. | Com | New build
21 | 1. Ground, Earthworks & Foundations | Collapse of excavation sides | Temporary batters ↔ Soil stability | Slope stability depends on soil type and moisture. | All | New build/Extension
22 | 1. Ground, Earthworks & Foundations | Excavation hits a sewer main | Earthworks ↔ Sewer network | Buried mains constrain where excavation can go. | All | All
23 | 1. Ground, Earthworks & Foundations | Existing footing exposed is smaller than assumed | New extension ↔ Existing footings | Extensions rely on the capacity of foundations nobody drew. | Res/Com | Extension/Refurb
24 | 1. Ground, Earthworks & Foundations | Differential settlement between old and new | Existing structure ↔ New extension | Different foundations settle at different rates. | Res/Com | Extension
25 | 1. Ground, Earthworks & Foundations | Underpinning needed to deepen basement | Existing footings ↔ New excavation | Lowering the floor removes support from existing walls. | Res/Com | Refurb/Upgrade
26 | 1. Ground, Earthworks & Foundations | Piling rig cannot access the site | Piling plant ↔ Site access | Heavy plant needs ground and clearance to operate. | Com/Ind | New build
27 | 1. Ground, Earthworks & Foundations | Piles driven out of position | Piles ↔ Pile cap design | Caps assume piles land within tolerance. | Com/Ind | New build
28 | 1. Ground, Earthworks & Foundations | Pile concrete defect found by integrity test | Pile shaft ↔ Load path | A defective pile cannot carry its design load. | Com/Ind | New build
29 | 1. Ground, Earthworks & Foundations | Heave of basement slab from uplift | Basement slab ↔ Groundwater | Water pressure lifts a lightly loaded slab. | Com | New build
30 | 1. Ground, Earthworks & Foundations | Tanking membrane punctured by reinforcement | Waterproofing ↔ Rebar | Membranes are fragile where steel and formwork pass. | Res/Com | New build
31 | 1. Ground, Earthworks & Foundations | Blinding concrete too soft to place rebar on | Footing base ↔ Subgrade | A stable platform is needed to set reinforcement accurately. | All | New build
32 | 1. Ground, Earthworks & Foundations | Trench footing collapses before the pour | Footing trench ↔ Soil | Open trenches fail in sand or wet soil. | Res | New build/Extension
33 | 1. Ground, Earthworks & Foundations | Footing steel cover wrong after trench trimming | Reinforcement ↔ Excavation | Cover depends on a level and accurate trench base. | Res | New build/Extension
34 | 1. Ground, Earthworks & Foundations | Termite activity found in the soil | Termite barrier ↔ Slab edge | Barrier continuity depends on the foundation detail. | Res | New build/Extension
35 | 1. Ground, Earthworks & Foundations | Plumbing stub-ups misplaced before the slab pour | Under-slab plumbing ↔ Slab | Services set before the pour cannot be moved afterwards. | Res | New build
36 | 1. Ground, Earthworks & Foundations | Under-slab conduit crushed by the pour | Electrical conduit ↔ Concrete | Embedded services must survive wet concrete loads. | All | New build
37 | 1. Ground, Earthworks & Foundations | Vapour barrier torn before the slab pour | Vapour membrane ↔ Slab | The membrane protects flooring from ground moisture. | Res/Com | New build
38 | 1. Ground, Earthworks & Foundations | Slab thickened where a trench crosses | Slab ↔ Service trench | Services cutting through slabs change the structural section. | Ind | New build
39 | 1. Ground, Earthworks & Foundations | Bore water found with high salinity | Footings/slab ↔ Groundwater chemistry | Salts attack concrete and reinforcement. | All | New build
40 | 1. Ground, Earthworks & Foundations | Sulfate attack on buried concrete | Concrete ↔ Soil chemistry | Concrete grade must suit the aggressive ground. | All | New build
41 | 1. Ground, Earthworks & Foundations | Steep site slips after clearing | Hillside structure ↔ Slope stability | Removing vegetation reduces natural stability. | Res | New build
42 | 1. Ground, Earthworks & Foundations | Retaining wall tilts after backfill | Retaining wall ↔ Backfill pressure | Wall design assumes drained controlled backfill. | Res/Com | All
43 | 1. Ground, Earthworks & Foundations | Retaining wall drains blocked | Retaining wall ↔ Drainage | Blocked drains build water pressure behind walls. | Res/Com | All
44 | 1. Ground, Earthworks & Foundations | Surcharge from a neighbour's building not known | Retention ↔ Adjoining loads | Retention designs include the loads pushing on it. | Com | New build
45 | 1. Ground, Earthworks & Foundations | Excavation exposes asbestos fragments in fill | Earthworks ↔ Hazmat | Asbestos in soil stops work and changes disposal. | All | All
46 | 1. Ground, Earthworks & Foundations | Rock hammering vibration damages a neighbour | Excavation method ↔ Adjacent buildings | Breaking rock transmits vibration through the ground. | Com | New build
47 | 1. Ground, Earthworks & Foundations | Dust and noise complaints halt earthworks | Excavation ↔ Environmental approvals | Permits limit how and when earthworks occur. | All | New build
48 | 1. Ground, Earthworks & Foundations | Borehole data shows variable bedrock level | Footing levels ↔ Bedrock | Foundations step to the rock they bear on. | Com/Ind | New build
49 | 1. Ground, Earthworks & Foundations | Cavities in limestone found under footing | Footings ↔ Karst ground | Voids reduce bearing below the footing. | Com/Ind | New build
50 | 1. Ground, Earthworks & Foundations | Organic peat layer discovered | Slab/footings ↔ Compressible soil | Peat compresses under load and over time. | Res/Ind | New build
51 | 1. Ground, Earthworks & Foundations | Compaction test fails on building pad | Slab base ↔ Subgrade compaction | A slab needs a compacted base to avoid settlement. | Ind/Res | New build
52 | 1. Ground, Earthworks & Foundations | Heavy racking loads exceed the slab design | Industrial slab ↔ Storage racking | Slab thickness is designed for the stored load. | Ind | All
53 | 1. Ground, Earthworks & Foundations | Forklift traffic wears joints in the slab | Industrial slab ↔ Joint design | Joints must withstand wheel impacts. | Ind | New build/Refurb
54 | 1. Ground, Earthworks & Foundations | Slab curls at joints | Slab ↔ Curing/shrinkage | Drying shrinkage lifts slab edges. | Ind/Com | New build
55 | 1. Ground, Earthworks & Foundations | Floor flatness fails for narrow aisle racking | Industrial slab ↔ Racking system | High-bay racking needs very flat floors. | Ind | New build
56 | 1. Ground, Earthworks & Foundations | Crane runway beam supports settle | Footings ↔ Overhead crane | Crane rails need precise stable support. | Ind | New build
57 | 1. Ground, Earthworks & Foundations | Heavy machinery pit hits groundwater | Machine pits ↔ Water table | Deep pits below the water table need tanking. | Ind | New build
58 | 1. Ground, Earthworks & Foundations | Machinery vibration shakes nearby footings | Machine foundations ↔ Building structure | Vibrating equipment needs isolated foundations. | Ind | All
59 | 1. Ground, Earthworks & Foundations | Tank farm bund too small for volume | Bunding ↔ Containment rules | Bunds are sized to hold the full tank volume. | Ind | New build
60 | 1. Ground, Earthworks & Foundations | Flood level raised by the authority | Floor levels ↔ Flood planning | Floor heights are fixed by flood levels. | Res/Com | New build/Extension
61 | 1. Ground, Earthworks & Foundations | Site cut/fill balance fails | Earthworks ↔ Site levels | Cut and fill should balance or cost rises. | All | New build
62 | 1. Ground, Earthworks & Foundations | Fill platform settles after construction | Building pad ↔ Fill consolidation | Fill consolidates and drops after placement. | Res/Ind | New build
63 | 1. Ground, Earthworks & Foundations | Stormwater runoff scours the batter | Landscape batter ↔ Drainage | Uncontrolled flow erodes cut and fill slopes. | All | New build
64 | 1. Ground, Earthworks & Foundations | Termite shield missed at slab penetrations | Pest barrier ↔ Plumbing | Every pipe through the slab is a pest path. | Res | New build
65 | 1. Ground, Earthworks & Foundations | Pier holes collapse in loose sand | Pier footings ↔ Soil | Open bores fail in unstable ground. | Res | New build/Extension
66 | 1. Ground, Earthworks & Foundations | Pier concrete poured into groundwater | Pier ↔ Water inflow | Concrete placed in water loses strength. | Res | New build/Extension
67 | 1. Ground, Earthworks & Foundations | Screw piles hit refusal early | Screw piles ↔ Hard strata | Piles must reach required depth to carry load. | Res | New build/Extension
68 | 1. Ground, Earthworks & Foundations | Footing rebar cage floats in the pour | Reinforcement ↔ Concrete placement | Steel must be tied and chaired to stay in position. | All | New build
69 | 1. Ground, Earthworks & Foundations | Pump line blocks during the pour | Concrete pump ↔ Mix design | The mix has to flow through the pump line. | Com | New build
70 | 1. Ground, Earthworks & Foundations | Delayed concrete truck causes a cold joint | Concrete supply ↔ Structural continuity | Delayed supply causes an unplanned joint. | All | New build
71 | 1. Ground, Earthworks & Foundations | Excavation spoil contaminated by mixing | Spoil ↔ Waste classification | Mixing clean and dirty soil raises disposal cost. | All | New build
72 | 1. Ground, Earthworks & Foundations | Ground vibration monitor alarm halts works | Excavation ↔ Monitoring limits | Limits protect adjoining buildings. | Com | New build
73 | 1. Ground, Earthworks & Foundations | Survey set-out error at the boundary | Setout ↔ Property line | Errors make the building encroach. | All | New build
74 | 1. Ground, Earthworks & Foundations | Neighbour's fence on the wrong boundary | Survey ↔ Site boundary | True boundaries can differ from fences. | Res | New build/Extension
75 | 1. Ground, Earthworks & Foundations | Easement prevents building over services | Footprint ↔ Property easements | Legal easements limit structure location. | Res/Com | New build/Extension
76 | 1. Ground, Earthworks & Foundations | Shared party wall footing discovered | New work ↔ Neighbour footing | Shared walls affect excavation near them. | Res/Com | Extension
77 | 1. Ground, Earthworks & Foundations | Existing slab too thin for new loads | New load ↔ Existing slab | Slab capacity is fixed by the old design. | Com/Ind | Refurb/Upgrade
78 | 1. Ground, Earthworks & Foundations | Old footings cracked under settlement | Existing footings ↔ New load path | Damaged footings cannot take added load. | Res | Refurb/Upgrade
79 | 1. Ground, Earthworks & Foundations | Basement walls not waterproofed originally | Existing basement ↔ Moisture | Older basements lack membranes. | Res/Com | Refurb/Upgrade
80 | 1. Ground, Earthworks & Foundations | Rising damp in old masonry foundations | Footings ↔ Damp course | Missing damp courses let ground moisture rise. | Res | Refurb/Upgrade
81 | 1. Ground, Earthworks & Foundations | Soil gas (methane/radon) detected | Slab ↔ Gas barrier | Ground gas needs barriers and ventilation. | Res/Com | New build
82 | 1. Ground, Earthworks & Foundations | Vapour intrusion from contaminated groundwater | Slab ↔ Groundwater contamination | Vapour enters through slab cracks and joints. | Com/Ind | New build
83 | 1. Ground, Earthworks & Foundations | Site cleared of trees creates erosion | Earthworks ↔ Sediment control | Bare soil washes into drains in rain. | All | New build
84 | 1. Ground, Earthworks & Foundations | Sediment basin overflows in storm | Site drainage ↔ Rain event | Basins must be sized for storm flows. | All | New build
85 | 1. Ground, Earthworks & Foundations | Spoil tip site closed by authority | Haulage ↔ Tip site | Disposal depends on an available site. | Com/Ind | New build
86 | 1. Ground, Earthworks & Foundations | Quarry product delivery delay | Earthworks ↔ Material supply | Roadbase and fill must arrive on schedule. | Ind/Com | New build
87 | 1. Ground, Earthworks & Foundations | Wet weather stops compaction works | Compaction ↔ Moisture | Soil must be near optimum moisture to compact. | Ind/Res | New build
88 | 1. Ground, Earthworks & Foundations | Bearing capacity lower after a wet winter | Footings ↔ Seasonal soil | Bearing strength varies with soil moisture. | Res | New build
89 | 1. Ground, Earthworks & Foundations | Contaminated groundwater needs treatment | Dewatering ↔ Water quality | Pumped water may need treatment before discharge. | Com/Ind | New build
90 | 1. Ground, Earthworks & Foundations | Retention shotcrete surface fails | Shotcrete wall ↔ Soil | Poor bond lets the wall delaminate. | Com | New build
91 | 1. Ground, Earthworks & Foundations | Heave from tree removal | Slab ↔ Soil moisture rebound | Soil expands when a tree no longer draws water. | Res | New build/Extension
92 | 1. Ground, Earthworks & Foundations | Construction traffic damages the street | Haulage ↔ Public road | Roads are repaired at the builder's cost. | All | New build
93 | 1. Ground, Earthworks & Foundations | Underpinning movement cracks existing plaster | Underpinning ↔ Existing finishes | Support changes move rigid finishes. | Res | Refurb/Upgrade
94 | 1. Ground, Earthworks & Foundations | Jet grout column misses design position | Ground improvement ↔ Footings | Improvement must sit under the load. | Com | New build
95 | 1. Ground, Earthworks & Foundations | Stone columns fail to improve soft soil | Ground improvement ↔ Soft soil | Improvement depends on soil response. | Ind/Res | New build
96 | 1. Ground, Earthworks & Foundations | Preloading takes longer than planned | Ground consolidation ↔ Programme | Soil consolidates on its own timeline. | Ind | New build
97 | 1. Ground, Earthworks & Foundations | Site noise limits reduce piling hours | Piling ↔ Neighbour amenity | Operating hours restrict output. | Com | New build
98 | 1. Ground, Earthworks & Foundations | Expansive soil moisture changes near a leaking pipe | Footings ↔ Plumbing leak | Leaks wet the soil locally and lift or drop footings. | Res | All
99 | 1. Ground, Earthworks & Foundations | Frost heave under unheated slab edges | Slab edge ↔ Frost | Freezing soil expands and lifts edges. | Ind/Res | New build
100 | 1. Ground, Earthworks & Foundations | Sinkhole or void opens near the excavation | Excavation ↔ Ground stability | Voids reduce support and endanger plant. | Com/Ind | New build
101 | 2. Structure & Structural Frame | Beam clashes with main duct | Structure ↔ HVAC | Structure needs continuity and ducts need a clear path. | Com | New build/Refurb
102 | 2. Structure & Structural Frame | Core drilling hits a post-tension tendon | PT slab ↔ Electrical/plumbing | Stressed tendons carry the slab and services cannot cut them. | Com/Res | New build/Refurb
103 | 2. Structure & Structural Frame | Slab drop leaves no fall for the drain | Structure ↔ Hydraulics | Gravity drainage needs height which structure consumes. | Com/Res | New build
104 | 2. Structure & Structural Frame | Slab penetrations missed before the pour | Concrete ↔ All services | Services must be located before structure sets. | All | New build
105 | 2. Structure & Structural Frame | Rebar too congested to pour | Reinforcement ↔ Concrete | Concrete can only work if it can flow around the steel. | Com/Ind | New build
106 | 2. Structure & Structural Frame | Formwork deflects during the pour | Formwork ↔ Structure | Temporary works shape the permanent structure. | Com/Res | New build
107 | 2. Structure & Structural Frame | Early shrinkage cracking | Concrete ↔ Waterproofing/finishes | Cracks propagate into anything bonded to the structure. | All | New build
108 | 2. Structure & Structural Frame | Steel fabrication error | Steel frame ↔ Façade | The frame sets the geometry the façade attaches to. | Com/Ind | New build
109 | 2. Structure & Structural Frame | Lift pit too shallow | Lift ↔ Structure | Lift travel depends on the pit and overrun the structure provides. | Com/Res | New build
110 | 2. Structure & Structural Frame | Lift shaft out of plumb | Lift ↔ Core walls | Rails need tight tolerance but the core is built loose. | Com/Res | New build
111 | 2. Structure & Structural Frame | Slab level tolerance exceeded | Slab ↔ Floor finishes | Finishes can only correct small variations. | All | New build
112 | 2. Structure & Structural Frame | Transfer beam deflects more than expected | Structure ↔ Partitions | Non-structural walls cannot follow structural movement. | Com/Res | New build
113 | 2. Structure & Structural Frame | Rooftop plant heavier than allowed | Roof structure ↔ Mechanical | Plant weight must match the capacity designed for it. | Com/Ind | All
114 | 2. Structure & Structural Frame | Stair geometry fails the code | Structure ↔ Egress | Structural dimensions determine safe exit. | All | New build
115 | 2. Structure & Structural Frame | Concrete cylinders fail strength test | Concrete supply ↔ Structural design | Design assumes the delivered concrete reaches its grade. | Com/Res | New build
116 | 2. Structure & Structural Frame | Concrete placed in hot weather sets too fast | Concrete ↔ Weather | Heat shortens working time and promotes cracking. | All | New build
117 | 2. Structure & Structural Frame | Concrete placed in cold weather freezes | Concrete ↔ Weather | Freezing disrupts hydration and strength gain. | All | New build
118 | 2. Structure & Structural Frame | Props removed too early | Formwork/props ↔ Young concrete | Concrete must gain strength before taking its own weight. | Com/Res | New build
119 | 2. Structure & Structural Frame | Slab edge forms burst | Edge formwork ↔ Concrete pressure | Wet concrete exerts hydrostatic pressure. | Com | New build
120 | 2. Structure & Structural Frame | Cover to reinforcement too thin | Rebar ↔ Durability | Cover protects steel from corrosion. | All | New build
121 | 2. Structure & Structural Frame | Reinforcement delivered to the wrong schedule | Rebar supply ↔ Pour programme | The pour waits on the right steel being in place. | Com | New build
122 | 2. Structure & Structural Frame | Post-tensioning stressed late | PT system ↔ Programme | Stressing releases propping and unlocks the next level. | Com/Res | New build
123 | 2. Structure & Structural Frame | Tendon sheath damaged | PT tendon ↔ Corrosion protection | Damaged ducts let moisture reach the tendon. | Com | New build
124 | 2. Structure & Structural Frame | Column out of position at set-out | Columns ↔ Floor plan | Columns constrain layouts above and below. | Com | New build
125 | 2. Structure & Structural Frame | Column too large for car park layout | Structure ↔ Parking | Columns reduce usable bays and aisles. | Com | New build
126 | 2. Structure & Structural Frame | Column reduced late to widen a corridor | Structure ↔ Egress | Smaller columns reduce capacity and fire rating. | Com | New build
127 | 2. Structure & Structural Frame | Shear wall opened for a new door | Shear walls ↔ Doors/services | Cutting a shear wall weakens lateral stability. | Com/Res | Refurb/Upgrade
128 | 2. Structure & Structural Frame | Precast panel dimension error | Precast ↔ Adjoining structure | Precast arrives finished and cannot be trimmed. | Ind/Com | New build
129 | 2. Structure & Structural Frame | Precast crane lift exceeds capacity | Precast panels ↔ Crane | Panel weight limits the crane reach. | Ind/Com | New build
130 | 2. Structure & Structural Frame | Precast panel damaged on delivery | Precast ↔ Logistics | Panels chip in transport and need repair. | Ind/Com | New build
131 | 2. Structure & Structural Frame | Tilt-up panel braces conflict with slab pours | Tilt-up panels ↔ Slab sequence | Bracing occupies the area the slab needs. | Ind | New build
132 | 2. Structure & Structural Frame | Tilt-up panel lift reveals cracking | Tilt panels ↔ Lifting inserts | Lifting stresses can crack thin panels. | Ind | New build
133 | 2. Structure & Structural Frame | Steel connection design changed after fabrication | Connections ↔ Fabricated steel | Revised loads change the connection details. | Com/Ind | New build
134 | 2. Structure & Structural Frame | Bolt holes do not align on site | Steel members ↔ Erection | Fabrication tolerance must match site tolerance. | Com/Ind | New build
135 | 2. Structure & Structural Frame | Weld inspection finds defects | Steel welds ↔ Structural capacity | Welds are the load path between members. | Com/Ind | New build
136 | 2. Structure & Structural Frame | Steel corrosion before coating | Steel ↔ Weather exposure | Uncoated steel rusts quickly in humid sites. | Ind/Com | New build
137 | 2. Structure & Structural Frame | Fireproofing damaged by following trades | Steel fire protection ↔ Services | Later trades knock off sprayed or board protection. | Com | New build
138 | 2. Structure & Structural Frame | Beam deflection cracks plasterboard ceiling | Steel beam ↔ Ceiling lining | Ceilings crack where beams flex. | Com/Res | New build
139 | 2. Structure & Structural Frame | Portal frame erected out of plumb | Portal frame ↔ Cladding | Cladding requires accurate frame lines. | Ind | New build
140 | 2. Structure & Structural Frame | Roof purlins overloaded by added plant | Purlins ↔ Rooftop equipment | Purlins are sized for light roof loads. | Ind | Refurb/Upgrade
141 | 2. Structure & Structural Frame | Mezzanine added without structural check | Mezzanine ↔ Existing frame | Added floors load columns and footings. | Ind/Com | Refurb/Upgrade
142 | 2. Structure & Structural Frame | Timber frame shrinks across floors | Timber frame ↔ Finishes | Drying timber shortens and moves finishes. | Res | New build
143 | 2. Structure & Structural Frame | Timber frame exposed to rain for weeks | Timber ↔ Weather | Wet timber swells, stains and grows mould. | Res | New build
144 | 2. Structure & Structural Frame | Engineered timber floor joist cut for a pipe | Floor joist ↔ Plumbing | Notching joists reduces their capacity. | Res | New build/Refurb
145 | 2. Structure & Structural Frame | Floor truss clashes with duct route | Truss ↔ HVAC | Trusses have fixed web layouts which restrict ducts. | Res | New build
146 | 2. Structure & Structural Frame | Floor deflection or bounce | Floor structure ↔ Occupant comfort | Span and stiffness affect perceived quality. | Res | New build
147 | 2. Structure & Structural Frame | Wall framing out of straight | Frame ↔ Plasterboard | Plaster shows frame waviness. | Res | New build
148 | 2. Structure & Structural Frame | Lintel undersized over a wide opening | Lintel ↔ Wall load | Openings concentrate load on the lintel. | Res | New build/Extension
149 | 2. Structure & Structural Frame | Brickwork cracks above openings | Masonry ↔ Lintel deflection | Lintel deflection cracks the brick above. | Res | New build
150 | 2. Structure & Structural Frame | Masonry movement joints omitted | Masonry ↔ Thermal movement | Masonry expands and contracts and needs joints. | Res/Com | New build
151 | 2. Structure & Structural Frame | Cavity wall ties missing | Masonry leaves ↔ Wall stability | Ties hold the outer leaf to the structure. | Res/Com | New build
152 | 2. Structure & Structural Frame | Block wall grout voids found | Reinforced masonry ↔ Load path | Voids reduce wall strength. | Com/Ind | New build
153 | 2. Structure & Structural Frame | Brick delivery colour mismatch | Masonry ↔ Appearance | Batch variation shows in finished walls. | Res/Com | All
154 | 2. Structure & Structural Frame | Existing wall removed is actually loadbearing | Existing walls ↔ Alterations | Old walls often carry unseen loads. | Res | Refurb/Upgrade
155 | 2. Structure & Structural Frame | Existing slab holes cut in wrong place | Existing slab ↔ New services | Old slabs hide reinforcement unknown to the builder. | Com | Refurb/Upgrade
156 | 2. Structure & Structural Frame | Concrete scanning misses rebar | Coring ↔ Existing reinforcement | Scans can fail to see every bar. | Com | Refurb/Upgrade
157 | 2. Structure & Structural Frame | Concrete cancer (spalling) found | Existing concrete ↔ Reinforcement corrosion | Corrosion expands steel and breaks concrete cover. | Com/Res | Refurb/Upgrade
158 | 2. Structure & Structural Frame | Existing steel corroded at connections | Old steel ↔ New loads | Section loss reduces capacity. | Ind/Com | Refurb/Upgrade
159 | 2. Structure & Structural Frame | Existing structure not built to drawings | As-built records ↔ Reality | Structural drawings may not match what was built. | All | Refurb/Upgrade
160 | 2. Structure & Structural Frame | Roof framing sagging | Old roof structure ↔ New roof cover | Heavier cover loads weak framing. | Res | Refurb/Upgrade
161 | 2. Structure & Structural Frame | Termite damage in timber frame | Timber ↔ Termites | Hidden damage reduces structural capacity. | Res | Refurb/Upgrade
162 | 2. Structure & Structural Frame | Rotted bearer found under the floor | Floor structure ↔ Moisture | Damp rot weakens support. | Res | Refurb/Upgrade
163 | 2. Structure & Structural Frame | Second storey added to a house | New storey ↔ Existing walls/footings | Existing structure was not designed for extra floors. | Res | Extension
164 | 2. Structure & Structural Frame | Extension tie-in misaligns floor levels | New slab ↔ Existing slab | Floor levels must meet at the junction. | Res | Extension
165 | 2. Structure & Structural Frame | Roof of extension drains into the existing roof | New roof ↔ Existing roof | Roof valleys and flashings must carry the added flow. | Res | Extension
166 | 2. Structure & Structural Frame | New structural opening in a heritage wall | Heritage fabric ↔ Structure | Alterations must preserve original material. | Res/Com | Refurb/Upgrade
167 | 2. Structure & Structural Frame | Seismic upgrade requires added bracing | Existing frame ↔ Seismic code | Old buildings lack ductile detailing. | Com | Refurb/Upgrade
168 | 2. Structure & Structural Frame | Façade ties corroded on old building | Old façade ↔ Backing structure | Corroded ties let façades detach. | Com | Refurb/Upgrade
169 | 2. Structure & Structural Frame | Slab thickness varies across the floor | Slab ↔ Services/finishes | Thin slabs limit chasing and anchors. | Com | Refurb/Upgrade
170 | 2. Structure & Structural Frame | Expansion joint cover missing | Structure joints ↔ Finishes | Joints must be bridged by movement covers. | Com/Ind | New build
171 | 2. Structure & Structural Frame | Differential movement between building wings | Separate structures ↔ Joint | Wings move independently and need gap allowances. | Com | New build
172 | 2. Structure & Structural Frame | Wind load on a high-bay shed underestimated | Wind loads ↔ Cladding fixings | Cladding must restrain suction forces. | Ind | New build
173 | 2. Structure & Structural Frame | Hail damage to roof sheeting | Roof sheeting ↔ Weather | Sheeting is the first line of defence. | Ind | All
174 | 2. Structure & Structural Frame | Roof drainage overflow blocked | Roof ↔ Eaves gutters | Blocked gutters overload roof structure with water. | Ind/Res | All
175 | 2. Structure & Structural Frame | Mezzanine vibration annoys occupants | Structure ↔ Occupant use | Lightweight floors vibrate under walking. | Com | New build
176 | 2. Structure & Structural Frame | Deck slab cracks above transfer girder | Slab ↔ Transfer structure | Transfer girders deflect and crack the slab. | Com | New build
177 | 2. Structure & Structural Frame | Shotcrete lining thickness falls short | Shotcrete ↔ Structural section | Thin lining reduces wall capacity. | Com | New build
178 | 2. Structure & Structural Frame | Fire-damaged structure needs assessment | Structure ↔ Fire exposure | Fire alters concrete and steel properties. | All | Refurb/Upgrade
179 | 2. Structure & Structural Frame | Blast or vehicle impact barrier required | Structure ↔ Security design | Security requirements add loads to the frame. | Com | New build/Refurb
180 | 2. Structure & Structural Frame | Crane hook height limits column heights | Overhead crane ↔ Building height | Crane lift envelope sets internal clearance. | Ind | New build
181 | 2. Structure & Structural Frame | Solar panel ballast overloads a flat roof | Roof slab ↔ PV ballast | Ballast adds heavy dead load. | Com/Ind | Refurb/Upgrade
182 | 2. Structure & Structural Frame | Rooftop terrace added to a flat roof | Roof slab ↔ New live load | Occupied roofs need higher capacity. | Res/Com | Refurb/Upgrade
183 | 2. Structure & Structural Frame | Planter boxes overload balconies | Balcony ↔ Landscape | Soil is heavy when wet. | Res | New build
184 | 2. Structure & Structural Frame | Balcony cantilever deflects | Balcony slab ↔ Door thresholds | Deflection affects drainage falls and doors. | Res | New build
185 | 2. Structure & Structural Frame | Balcony balustrade fixings pull out | Balustrade ↔ Slab edge | Edge loads need robust anchors. | Res | New build
186 | 2. Structure & Structural Frame | Glass balustrade requires slab edge upgrade | Glass barrier ↔ Edge structure | Barrier loads concentrate at the slab edge. | Res/Com | New build
187 | 2. Structure & Structural Frame | Car park slab fails vehicle loads | Car park slab ↔ Vehicle load | Parking structures face heavy concentrated wheel loads. | Com/Res | New build
188 | 2. Structure & Structural Frame | Ramp gradient steeper than allowed | Car park ramp ↔ Vehicle clearance | Ramp geometry controls car scraping. | Com/Res | New build
189 | 2. Structure & Structural Frame | Headroom beneath a beam below minimum | Structure ↔ Vehicle clearance | Beams reduce usable height for vehicles. | Com/Res | New build
190 | 2. Structure & Structural Frame | Construction loads exceed the slab's early-age capacity | Slab ↔ Construction loading | Young concrete cannot carry stacked materials. | Com/Res | New build
191 | 2. Structure & Structural Frame | Reshoring sequence not followed | Props ↔ Upper slabs | Loads travel through temporary props to lower floors. | Com/Res | New build
192 | 2. Structure & Structural Frame | Concrete pump line weight overloads the formwork | Formwork ↔ Pumping equipment | Pump lines add load to decks. | Com | New build
193 | 2. Structure & Structural Frame | Hot work ignites combustible formwork or panels | Temporary works ↔ Fire | Welding sparks start fires in stored materials. | Com | New build
194 | 2. Structure & Structural Frame | Precast stair units do not fit landings | Precast stairs ↔ Core walls | Precast needs accurate landings. | Com/Res | New build
195 | 2. Structure & Structural Frame | Cast-in plates misplaced for steel connections | Concrete ↔ Steel | Steel connections rely on accurate embedded plates. | Com/Ind | New build
196 | 2. Structure & Structural Frame | Post-installed anchors fail pull-out tests | Anchors ↔ Concrete | Anchors depend on concrete condition and edge distance. | All | All
197 | 2. Structure & Structural Frame | Slab-on-ground cracks at re-entrant corners | Slab ↔ Reinforcement detailing | Corners concentrate stress. | Res/Ind | New build
198 | 2. Structure & Structural Frame | Thermal expansion of long roof sheets | Roof structure ↔ Cladding | Long runs need allowance for movement. | Ind | New build
199 | 2. Structure & Structural Frame | Wind uplift pulls the roof at the eave | Roof framing ↔ Tie-downs | Tie-downs complete the wind load path. | Res | New build
200 | 2. Structure & Structural Frame | Wall bracing removed for a large window | Bracing ↔ Window openings | Bracing resists lateral loads. | Res | New build/Extension
201 | 3. Building Envelope & Waterproofing | Windows delivered to the wrong size | Glazing ↔ Structural openings | Openings are built first and glazing must fit their tolerance. | All | New build/Extension
202 | 3. Building Envelope & Waterproofing | Slab edge out of line | Structure ↔ Curtain wall brackets | Façade fixings assume the edge is accurate. | Com | New build
203 | 3. Building Envelope & Waterproofing | Leak at window head | Glazing ↔ Waterproofing | Glazing is only as watertight as its flashing interface. | All | All
204 | 3. Building Envelope & Waterproofing | Roof membrane punctured by later trades | Roofing ↔ Plant/services | Penetrations are weak points in the weatherproof layer. | Com/Ind | All
205 | 3. Building Envelope & Waterproofing | Condensation inside the wall | Insulation ↔ HVAC | Indoor humidity and temperature drive where moisture condenses. | Res/Com | New build/Refurb
206 | 3. Building Envelope & Waterproofing | Thermal bridge at balcony slabs | Structure ↔ Thermal envelope | Continuous structure conducts heat through the insulation. | Res | New build
207 | 3. Building Envelope & Waterproofing | Cladding product discontinued | Façade ↔ Fire compliance | A substitute material changes fire performance. | Res/Com | New build
208 | 3. Building Envelope & Waterproofing | Gale damages the unclad frame | Temporary protection ↔ Envelope | The envelope is not weather-ready until complete. | All | New build/Extension
209 | 3. Building Envelope & Waterproofing | Movement joints omitted | Façade ↔ Structure | Structure moves and the façade needs room to follow. | Com | New build
210 | 3. Building Envelope & Waterproofing | Efflorescence on brickwork | Masonry ↔ Moisture control | Water carries salts through porous material. | Res/Com | All
211 | 3. Building Envelope & Waterproofing | Roof ponding | Roof ↔ Stormwater | Falls and outlets must carry water away. | Com/Ind | All
212 | 3. Building Envelope & Waterproofing | Balcony leaks onto the apartment below | Waterproofing ↔ Tiling | Finishes hide the membrane that must stay intact. | Res | New build
213 | 3. Building Envelope & Waterproofing | Party wall fails the acoustic test | Walls ↔ Acoustics/services | Sound flanks through services and joints. | Res | New build
214 | 3. Building Envelope & Waterproofing | Air-tightness test fails | Envelope ↔ HVAC | HVAC sizing assumes an airtight shell. | Com/Res | New build
215 | 3. Building Envelope & Waterproofing | Roof sheeting fixing pattern wrong | Roof sheeting ↔ Wind uplift | Fixings must resist wind suction at edges. | Ind/Res | New build
216 | 3. Building Envelope & Waterproofing | Roof sheet laps leak at low pitch | Roof sheeting ↔ Roof pitch | Minimum pitch is needed to shed water over laps. | Ind | New build
217 | 3. Building Envelope & Waterproofing | Skylight leak after installation | Skylight ↔ Roof membrane | Skylight kerbs must tie into the roof waterproofing. | Res/Com | All
218 | 3. Building Envelope & Waterproofing | Skylight overheats the interior | Glazing ↔ HVAC load | Solar gains add cooling load. | Com/Ind | All
219 | 3. Building Envelope & Waterproofing | Gutter fall incorrect and water overflows | Gutter ↔ Fascia/structure | Gutters rely on accurate fall and outlets. | Res | New build
220 | 3. Building Envelope & Waterproofing | Box gutter overflows into the ceiling | Roof drainage ↔ Ceiling space | Hidden gutters leak into the building when blocked. | Res/Com | All
221 | 3. Building Envelope & Waterproofing | Flashing missing at roof-wall junction | Roof ↔ Wall cladding | Junction flashings are the primary leak path. | Res/Com | New build
222 | 3. Building Envelope & Waterproofing | Parapet cap flashing fails | Parapet ↔ Waterproofing | Parapets expose both faces to the weather. | Com | All
223 | 3. Building Envelope & Waterproofing | Roof insulation compressed by foot traffic | Insulation ↔ Roof access | Crushed insulation loses R-value. | Com/Ind | All
224 | 3. Building Envelope & Waterproofing | Spray foam insulation off-gasses | Insulation ↔ Indoor air | Chemical products require cure time before occupation. | Res | New build/Refurb
225 | 3. Building Envelope & Waterproofing | Insulation installed over wiring creates a hazard | Insulation ↔ Electrical | Cable heat needs dissipation. | Res | Refurb/Upgrade
226 | 3. Building Envelope & Waterproofing | Insulation batts left out behind services | Insulation ↔ Services | Services block continuous insulation. | Res | New build
227 | 3. Building Envelope & Waterproofing | Wall wrap torn and not taped | Building wrap ↔ Framing | Wrap provides secondary weather protection. | Res | New build
228 | 3. Building Envelope & Waterproofing | Cladding installed over wet framing | Cladding ↔ Timber frame | Trapped moisture rots framing. | Res | New build
229 | 3. Building Envelope & Waterproofing | Rain screen cavity blocked with debris | Cladding ↔ Cavity ventilation | Cavities must drain and dry. | Res/Com | New build
230 | 3. Building Envelope & Waterproofing | Cladding panels differ in colour batch | Cladding ↔ Appearance | Batch variation shows on large façades. | Com | New build
231 | 3. Building Envelope & Waterproofing | Cladding fixings not corrosion-rated for coast | Cladding fixings ↔ Marine environment | Salt air corrodes standard fixings. | Res/Com | New build
232 | 3. Building Envelope & Waterproofing | Façade bracket thermal break missing | Façade bracket ↔ Insulation | Brackets bridge the insulation layer. | Com | New build
233 | 3. Building Envelope & Waterproofing | Curtain wall unitised panel delivery late | Façade ↔ Programme | Façade completion enables internal trades. | Com | New build
234 | 3. Building Envelope & Waterproofing | Curtain wall water test fails | Curtain wall ↔ Sealants | Sealants and gaskets provide the water barrier. | Com | New build
235 | 3. Building Envelope & Waterproofing | Glass panel breaks during installation | Glazing ↔ Handling | Large panels are fragile to place. | Com | New build
236 | 3. Building Envelope & Waterproofing | Nickel sulfide glass breakage | Toughened glass ↔ Heat | Hidden inclusions can fail later. | Com | All
237 | 3. Building Envelope & Waterproofing | Glass thermal stress cracks | Glazing ↔ Shading/heating | Uneven temperature stresses glass edges. | Com | New build
238 | 3. Building Envelope & Waterproofing | Glass spec changed to improve acoustics | Glass ↔ Frame design | Thicker glass is heavier and needs stronger frames. | Com | New build
239 | 3. Building Envelope & Waterproofing | Window frames thermally bridged | Window frame ↔ Energy rating | Aluminium conducts heat through the frame. | Res | New build
240 | 3. Building Envelope & Waterproofing | Window installation out of square | Window ↔ Wall opening | Out-of-square openings cause binding and leaks. | Res | All
241 | 3. Building Envelope & Waterproofing | Window sill flashing reversed | Window ↔ Wall cladding | Sill flashing must shed water outward. | Res | New build
242 | 3. Building Envelope & Waterproofing | Sliding door track floods | Sliding door ↔ Threshold drainage | Tracks need drainage to the outside. | Res | New build
243 | 3. Building Envelope & Waterproofing | Balcony door threshold too high | Door ↔ Waterproofing upturn | Waterproofing upturns raise thresholds. | Res | New build
244 | 3. Building Envelope & Waterproofing | Door threshold fails accessibility | Door ↔ Floor level | Level thresholds need hidden drainage. | Res/Com | New build
245 | 3. Building Envelope & Waterproofing | External door warps in sun | Door ↔ Climate | Dark doors on sun faces warp. | Res | All
246 | 3. Building Envelope & Waterproofing | Shopfront glazing installed before slab complete | Shopfront ↔ Slab levels | Glazing needs final floor levels to set. | Com | New build
247 | 3. Building Envelope & Waterproofing | Roller shutter fixings foul on structure | Shutter ↔ Structure | Shutters need clear mounting. | Ind | New build
248 | 3. Building Envelope & Waterproofing | Loading dock door seals fail | Dock doors ↔ Dock leveller | Seals depend on dock height and truck geometry. | Ind | New build
249 | 3. Building Envelope & Waterproofing | Dock leveller pit floods | Dock leveller ↔ Drainage | Pits collect water without drainage. | Ind | New build
250 | 3. Building Envelope & Waterproofing | Industrial cladding dents from forklift | Cladding ↔ Operations | Low panels need protection. | Ind | All
251 | 3. Building Envelope & Waterproofing | Translucent roof sheets crack | Roof sheeting ↔ UV | UV degrades plastic sheeting. | Ind | All
252 | 3. Building Envelope & Waterproofing | Ridge vent leaks in wind-driven rain | Roof ventilation ↔ Weatherproofing | Vents trade airflow for weather exposure. | Ind/Res | New build
253 | 3. Building Envelope & Waterproofing | Whirlybird vent noise | Roof vent ↔ Occupants | Spinning vents transmit noise. | Res | All
254 | 3. Building Envelope & Waterproofing | Roof insulation blocks eaves ventilation | Insulation ↔ Roof ventilation | Insulation must leave air paths. | Res | Refurb/Upgrade
255 | 3. Building Envelope & Waterproofing | Attic condensation | Roof space ↔ Moisture | Warm moist air meets cold roof surfaces. | Res | All
256 | 3. Building Envelope & Waterproofing | Green roof overloads waterproofing | Green roof ↔ Waterproofing | Soil load and roots stress membranes. | Com/Res | New build
257 | 3. Building Envelope & Waterproofing | Root penetration of roof membrane | Roof garden ↔ Waterproofing | Root barriers are needed. | Com/Res | New build
258 | 3. Building Envelope & Waterproofing | Pavers on pedestals unstable on the roof | Roof paving ↔ Roof drainage | Support systems must allow drainage. | Com/Res | New build
259 | 3. Building Envelope & Waterproofing | Membrane upstand too low at the door | Waterproofing ↔ Door thresholds | Upstand height is set by code. | Res/Com | New build
260 | 3. Building Envelope & Waterproofing | Waterproofing test (flood test) fails | Waterproofing ↔ Concrete | Flood tests reveal leaks before tiling. | Res/Com | New build
261 | 3. Building Envelope & Waterproofing | Wet area membrane cure time ignored | Membrane ↔ Tiling programme | Membranes must cure before tiling. | Res | New build
262 | 3. Building Envelope & Waterproofing | Shower recess waterproofing detail wrong | Wet area ↔ Floor waste | Falls and membranes must meet at the drain. | Res | New build
263 | 3. Building Envelope & Waterproofing | Bathroom exhaust vented into the roof space | Exhaust ↔ Roof space | Moist air must go outside. | Res | New build
264 | 3. Building Envelope & Waterproofing | Mould behind wet walls | Wall lining ↔ Moisture | Moist cavities support mould growth. | Res | All
265 | 3. Building Envelope & Waterproofing | Rising damp after render added | Old masonry ↔ Render | Impervious render traps moisture. | Res | Refurb/Upgrade
266 | 3. Building Envelope & Waterproofing | Lime mortar replaced with cement mortar | Heritage masonry ↔ Mortar | Hard mortar damages soft brick. | Res/Com | Refurb/Upgrade
267 | 3. Building Envelope & Waterproofing | Painted brick cannot breathe | Heritage masonry ↔ Coatings | Non-breathable paint traps moisture. | Res | Refurb/Upgrade
268 | 3. Building Envelope & Waterproofing | Asbestos cladding disturbed | Old cladding ↔ Hazmat | Asbestos sheets release fibres when cut. | Res/Ind | Refurb/Upgrade
269 | 3. Building Envelope & Waterproofing | Lead paint found on old windows | Old finishes ↔ Hazmat | Sanding releases toxic dust. | Res | Refurb/Upgrade
270 | 3. Building Envelope & Waterproofing | Single glazing replaced with double and frames cannot carry it | Window frames ↔ Glass weight | Heavier glass needs new frames. | Res | Refurb/Upgrade
271 | 3. Building Envelope & Waterproofing | Retrofit insulation causes dampness | Wall cavity ↔ Insulation | Cavity fill can bridge moisture. | Res | Refurb/Upgrade
272 | 3. Building Envelope & Waterproofing | Overcladding hides defects | Overcladding ↔ Substrate | New cladding relies on the old substrate. | Com/Res | Refurb/Upgrade
273 | 3. Building Envelope & Waterproofing | Overcladding load exceeds old fixings | Old wall ↔ New cladding | Wall fixings were not designed for added weight. | Com/Res | Refurb/Upgrade
274 | 3. Building Envelope & Waterproofing | New extension roof lines do not match existing | New roof ↔ Existing roof | Matching pitches and materials require care. | Res | Extension
275 | 3. Building Envelope & Waterproofing | Extension wall flashing cannot tie into old cladding | New wall ↔ Old cladding | Different systems make junctions hard to seal. | Res | Extension
276 | 3. Building Envelope & Waterproofing | Extension window sizes differ from existing | New windows ↔ Existing facade | Old units have different dimensions. | Res | Extension
277 | 3. Building Envelope & Waterproofing | Termite shield bridged by new render | Termite barrier ↔ Render | Render can hide the inspection gap. | Res | New build/Extension
278 | 3. Building Envelope & Waterproofing | Slab edge exposed or covered incorrectly | Slab edge ↔ Cladding | Exposed edges allow moisture or termite entry. | Res | New build
279 | 3. Building Envelope & Waterproofing | Wind-driven rain enters weep holes | Masonry weep holes ↔ Wind | Weeps drain water but admit wind. | Res | New build
280 | 3. Building Envelope & Waterproofing | Garage door opening sag | Garage door ↔ Lintel | Lintel deflection binds the door. | Res | New build
281 | 3. Building Envelope & Waterproofing | Vehicle impact damages a façade column | Façade ↔ Vehicle access | Protection is needed at car park interfaces. | Com | All
282 | 3. Building Envelope & Waterproofing | Louvre blades block fire exit air | Louvre ↔ Ventilation | Louvre free area controls airflow. | Com | New build
283 | 3. Building Envelope & Waterproofing | Louvre leaks in storms | Louvre ↔ Weatherproofing | Louvres admit water at high wind speeds. | Com/Ind | New build
284 | 3. Building Envelope & Waterproofing | Operable window cannot open due to wind code | Windows ↔ Wind pressure | Tall buildings need restricted openings. | Com | New build
285 | 3. Building Envelope & Waterproofing | External shading affects wind loads | Shading devices ↔ Façade | Shading adds area for wind pressure. | Com | New build
286 | 3. Building Envelope & Waterproofing | Façade cleaning access not provided | Façade ↔ Maintenance | High façades need anchors and cradles. | Com | New build
287 | 3. Building Envelope & Waterproofing | Window cleaning anchors fail the test | Roof anchors ↔ Structure | Anchors must connect to proper structure. | Com/Res | New build
288 | 3. Building Envelope & Waterproofing | Sealant joint movement exceeds capacity | Sealants ↔ Façade movement | Sealants fail if joints move too far. | Com | New build
289 | 3. Building Envelope & Waterproofing | Sealant incompatible with stone | Sealant ↔ Natural stone | Some sealants stain stone. | Com | New build
290 | 3. Building Envelope & Waterproofing | Stone cladding fixing pull-out failure | Stone cladding ↔ Backing | Stone anchors depend on substrate strength. | Com | New build
291 | 3. Building Envelope & Waterproofing | Stone slab delivered chipped | Stone supply ↔ Finishing programme | Delivery damage delays installation. | Com/Res | New build
292 | 3. Building Envelope & Waterproofing | Cladding panels fail impact test | Cladding ↔ Compliance testing | Test results decide what products are allowed. | Com | New build
293 | 3. Building Envelope & Waterproofing | Façade engineering not coordinated with structure deflection | Façade ↔ Structure movement | Façade must accommodate slab deflections. | Com | New build
294 | 3. Building Envelope & Waterproofing | Wind-driven rain enters via window frame corners | Window frames ↔ Seals | Corner joints are weak points. | Res | All
295 | 3. Building Envelope & Waterproofing | Gutter guard fails in bushfire | Gutter ↔ Bushfire | Combustible guards ignite. | Res | All
296 | 3. Building Envelope & Waterproofing | Sarking omitted under metal roofing | Roof ↔ Condensation | Sarking controls condensation and dust. | Res | New build
297 | 3. Building Envelope & Waterproofing | Roof tiles break from foot traffic | Roof tiles ↔ Access | Services trades walk on roofs. | Res | All
298 | 3. Building Envelope & Waterproofing | Eaves gaps allow rodent entry | Eaves ↔ Pest control | Gaps let vermin into roof spaces. | Res | All
299 | 3. Building Envelope & Waterproofing | Window film voids glass warranty | Glazing ↔ Heat build-up | Films increase thermal stress. | Res/Com | Refurb/Upgrade
300 | 3. Building Envelope & Waterproofing | Retrofit double glazing in heritage frames | Heritage windows ↔ Energy upgrade | Heritage frames cannot carry heavy glass. | Res | Refurb/Upgrade
301 | 4. Fire, Life Safety & Compliance | Fire collar missing at a pipe penetration | Fire compartments ↔ Services | Every service hole must preserve compartment integrity. | All | All
302 | 4. Fire, Life Safety & Compliance | Sprinkler head blocked by a beam | Fire services ↔ Structure | Spray patterns need clear space. | Com/Ind | New build
303 | 4. Fire, Life Safety & Compliance | Ductwork shadows sprinkler coverage | Sprinklers ↔ HVAC | Ducts block water as well as air. | Com/Ind | All
304 | 4. Fire, Life Safety & Compliance | Hydrant pressure insufficient | Fire services ↔ Water supply | Fire systems depend on the supply capacity of the hydraulic main. | Com/Ind | New build
305 | 4. Fire, Life Safety & Compliance | Smoke control fails commissioning | Fire ↔ HVAC/BMS | Fans and dampers must behave as fire systems on cue. | Com | New build
306 | 4. Fire, Life Safety & Compliance | Fire door gaps out of tolerance | Doors ↔ Compartmentation | A rating only holds if the installation matches the tested one. | All | All
307 | 4. Fire, Life Safety & Compliance | Design change reduces structural fire rating | Structure ↔ Fire engineering | Structure must survive fire long enough for egress. | Com | New build
308 | 4. Fire, Life Safety & Compliance | Column narrows the exit path | Structure ↔ Egress | Structure occupies space the exit width needs. | Com | New build
309 | 4. Fire, Life Safety & Compliance | Fire alarm cable not fire-rated | Electrical ↔ Fire systems | Alarms must function during the event they detect. | Com/Ind | New build
310 | 4. Fire, Life Safety & Compliance | Cladding fails the fire test | Façade ↔ Fire safety | The exterior must not spread fire up the building. | Res/Com | New build/Refurb
311 | 4. Fire, Life Safety & Compliance | Fire-rated wall stops at the ceiling not the slab | Wall ↔ Roof/slab above | Compartment walls must run slab to slab. | Com/Res | All
312 | 4. Fire, Life Safety & Compliance | Fire rated shaft penetrated by cable tray | Fire shaft ↔ Electrical | Penetrations compromise shaft rating. | Com | All
313 | 4. Fire, Life Safety & Compliance | Fire damper missing in a rated duct | HVAC ↔ Fire compartment | Dampers close ducts at fire walls. | Com | New build
314 | 4. Fire, Life Safety & Compliance | Fire damper inaccessible for testing | Fire damper ↔ Ceilings | Dampers need access for annual testing. | Com | New build
315 | 4. Fire, Life Safety & Compliance | Intumescent paint thickness insufficient | Steel ↔ Fire protection | Thickness decides the fire resistance period. | Com/Ind | New build
316 | 4. Fire, Life Safety & Compliance | Fire stopping at the façade-slab gap missing | Façade ↔ Slab edge | Cavity fires spread through perimeter gaps. | Res/Com | New build
317 | 4. Fire, Life Safety & Compliance | Fire-rated glazing replaced with ordinary glass | Glazing ↔ Fire compartment | Glass loses integrity in fire. | Com | All
318 | 4. Fire, Life Safety & Compliance | Exit door swings against egress travel | Doors ↔ Egress | Egress doors swing in the exit direction. | Com | New build
319 | 4. Fire, Life Safety & Compliance | Exit sign hidden by services | Exit signage ↔ Ceiling services | Signs must be visible from travel paths. | Com | New build
320 | 4. Fire, Life Safety & Compliance | Emergency lighting illumination levels fail | Emergency lighting ↔ Layout | Lighting must meet minimum lux on exit paths. | Com | New build
321 | 4. Fire, Life Safety & Compliance | Egress corridor narrowed by a fit-out | Fit-out ↔ Egress width | Tenant works must not reduce exit width. | Com | Refurb/Upgrade
322 | 4. Fire, Life Safety & Compliance | Travel distance exceeds the limit | Floor layout ↔ Exit location | Maximum travel to an exit constrains layouts. | Com/Ind | New build/Refurb
323 | 4. Fire, Life Safety & Compliance | Stair pressurisation fan too weak | Stair ↔ Mechanical | Pressurisation keeps smoke out of exit stairs. | Com | New build
324 | 4. Fire, Life Safety & Compliance | Stair doors do not close because of pressure | Stair ↔ Door closers | Pressure can prevent doors closing. | Com | New build
325 | 4. Fire, Life Safety & Compliance | Lift lobby smoke seal fails | Lift ↔ Smoke control | Lift shafts spread smoke between floors. | Com | New build
326 | 4. Fire, Life Safety & Compliance | Fire lift power supply not segregated | Fire lift ↔ Electrical | Fire lifts need protected supplies. | Com | New build
327 | 4. Fire, Life Safety & Compliance | Fire pump room flooded | Fire pump ↔ Drainage | Pump rooms must stay operational in flooding. | Com | New build
328 | 4. Fire, Life Safety & Compliance | Fire pump fails flow test | Fire pump ↔ Hydraulic design | Pumps must deliver the designed flow. | Com | New build
329 | 4. Fire, Life Safety & Compliance | Sprinkler pipework not pressure tested before ceilings | Sprinklers ↔ Ceiling programme | Leaks must be found before concealment. | Com | New build
330 | 4. Fire, Life Safety & Compliance | Sprinkler head painted over | Sprinklers ↔ Painting | Paint on heads can prevent operation. | Com | All
331 | 4. Fire, Life Safety & Compliance | Sprinkler layout misses a coverage zone | Sprinklers ↔ Floor layout | Layout changes can leave gaps. | Com | Refurb/Upgrade
332 | 4. Fire, Life Safety & Compliance | Tenant partitions block sprinkler spray | Sprinklers ↔ Partitions | Walls change coverage areas. | Com | Refurb/Upgrade
333 | 4. Fire, Life Safety & Compliance | Sprinkler water supply upgraded by the authority | Sprinklers ↔ Mains | Fire flow demands exceed the existing mains. | Com/Ind | New build
334 | 4. Fire, Life Safety & Compliance | High-hazard storage requires upgraded sprinklers | Fire protection ↔ Warehouse use | Stored commodity decides sprinkler design. | Ind | Refurb/Upgrade
335 | 4. Fire, Life Safety & Compliance | Racking height above sprinkler rating | Storage racking ↔ Fire protection | Racks above design height defeat sprinklers. | Ind | Refurb/Upgrade
336 | 4. Fire, Life Safety & Compliance | Fire hose reel coverage gap | Hose reels ↔ Layout | Reels must reach all areas. | Com/Ind | New build
337 | 4. Fire, Life Safety & Compliance | Fire hydrant booster position clashes with landscape | Fire booster ↔ Site layout | Boosters need clear access for fire brigade. | Com | New build
338 | 4. Fire, Life Safety & Compliance | Fire brigade access road too narrow | Site layout ↔ Fire access | Appliances need turning and width. | Com/Ind | New build
339 | 4. Fire, Life Safety & Compliance | Fire alarm detectors obstructed by new ductwork | Detectors ↔ HVAC | Duct and air flow alter detector coverage. | Com | Refurb/Upgrade
340 | 4. Fire, Life Safety & Compliance | Detectors triggered by construction dust | Fire alarm ↔ Construction | Dust causes false alarms. | Com | Refurb/Upgrade
341 | 4. Fire, Life Safety & Compliance | Fire alarm panel cannot integrate with new systems | Fire alarm ↔ BMS | Interfaces must be compatible. | Com | Refurb/Upgrade
342 | 4. Fire, Life Safety & Compliance | Smoke alarms interconnection fails | Smoke alarms ↔ Electrical | Interconnected alarms need a reliable circuit. | Res | New build
343 | 4. Fire, Life Safety & Compliance | Smoke alarm location conflicts with ceiling fans | Smoke alarms ↔ Fans | Airflow can keep smoke from reaching alarms. | Res | New build
344 | 4. Fire, Life Safety & Compliance | Bushfire rating (BAL) increased late | Envelope ↔ Bushfire design | BAL decides materials for glass, cladding and decks. | Res | New build/Extension
345 | 4. Fire, Life Safety & Compliance | Ember-protection mesh blocks ventilation | Bushfire mesh ↔ Ventilation | Fine mesh restricts airflow. | Res | New build
346 | 4. Fire, Life Safety & Compliance | Decking material not suitable for bushfire zone | Deck ↔ Bushfire rating | Combustible timber is restricted. | Res | New build/Extension
347 | 4. Fire, Life Safety & Compliance | Gas cylinder near an opening in a fire zone | Gas storage ↔ Fire safety | Cylinders need separation distances. | Res/Ind | All
348 | 4. Fire, Life Safety & Compliance | Flammable liquids store non-compliant | Hazardous goods ↔ Building layout | Storage rooms need ratings and bunding. | Ind | New build
349 | 4. Fire, Life Safety & Compliance | Kitchen exhaust duct not fire-rated | Kitchen ventilation ↔ Fire safety | Grease fires travel in ducts. | Com | New build/Refurb
350 | 4. Fire, Life Safety & Compliance | Commercial kitchen hood suppression missing | Kitchen ↔ Fire suppression | Hoods need suppression over cookers. | Com | New build/Refurb
351 | 4. Fire, Life Safety & Compliance | Waste chute fire rating not achieved | Waste chute ↔ Fire design | Chutes connect floors and spread fire. | Res | New build
352 | 4. Fire, Life Safety & Compliance | Garbage room fire sprinkler omitted | Waste room ↔ Fire suppression | Waste rooms are high fire load areas. | Res/Com | New build
353 | 4. Fire, Life Safety & Compliance | Car park ventilation fails smoke test | Car park ↔ Ventilation | Smoke clearance protects egress. | Res/Com | New build
354 | 4. Fire, Life Safety & Compliance | Fire engineering solution rejected by the authority | Performance solution ↔ Approval | Alternative solutions need regulator approval. | Com | New build/Refurb
355 | 4. Fire, Life Safety & Compliance | Fire-rating of existing floor unknown | Old slab ↔ Fire code | Old structures may not satisfy current codes. | Com | Refurb/Upgrade
356 | 4. Fire, Life Safety & Compliance | Change of use triggers full fire upgrade | Building use ↔ Fire code | New use classes bring stricter fire rules. | Res/Com | Refurb/Upgrade
357 | 4. Fire, Life Safety & Compliance | Heritage building cannot fit fire stairs | Heritage fabric ↔ Egress | Added stairs conflict with historic plan. | Com | Refurb/Upgrade
358 | 4. Fire, Life Safety & Compliance | Timber floors lack fire separation | Old floors ↔ Fire compartments | Timber floors burn through quickly. | Res/Com | Refurb/Upgrade
359 | 4. Fire, Life Safety & Compliance | Combustible insulation panels discovered | Insulation ↔ Fire safety | Foam panels can be a fire risk. | Ind/Com | Refurb/Upgrade
360 | 4. Fire, Life Safety & Compliance | Roof space lacks fire separation | Roof void ↔ Fire spread | Fire spreads along open roof spaces. | Res | Refurb/Upgrade
361 | 4. Fire, Life Safety & Compliance | Party wall in roof space missing | Townhouse roofs ↔ Fire separation | Fire walls must extend through the roof. | Res | New build
362 | 4. Fire, Life Safety & Compliance | Fire-rated wall penetrated by power outlets back-to-back | Wall ↔ Electrical | Opposed outlets compromise wall rating. | Res | New build
363 | 4. Fire, Life Safety & Compliance | Downlights penetrate rated ceilings | Lighting ↔ Fire-rated ceiling | Fittings need rated covers. | Res | New build
364 | 4. Fire, Life Safety & Compliance | Exhaust fan duct through a fire wall | Ventilation ↔ Fire wall | Ducts need rated enclosures. | Res | New build
365 | 4. Fire, Life Safety & Compliance | Fire hydrant test shows poor pressure | Hydrants ↔ Street mains | The street network may not provide the flow assumed. | Com/Ind | New build
366 | 4. Fire, Life Safety & Compliance | Building height triggers extra fire measures | Building height ↔ Fire code | Greater height needs more fire safety. | Com/Res | New build
367 | 4. Fire, Life Safety & Compliance | Occupant load exceeds the exit capacity | Occupancy ↔ Egress | Exit widths cap the people allowed. | Com | Refurb/Upgrade
368 | 4. Fire, Life Safety & Compliance | Mezzanine added triggers new egress | Mezzanine ↔ Egress | New floor area adds exits and distances. | Ind/Com | Refurb/Upgrade
369 | 4. Fire, Life Safety & Compliance | Accessible toilet cannot fit the structure | Accessibility ↔ Plan | Accessible rooms need clearances. | Com | New build/Refurb
370 | 4. Fire, Life Safety & Compliance | Lift too small for a stretcher | Lift ↔ Accessibility/emergency | Minimum lift sizes are mandated. | Com/Res | New build
371 | 4. Fire, Life Safety & Compliance | Ramp gradient exceeds accessible limit | Ramp ↔ Site levels | Site levels limit accessible slopes. | Com/Res | New build
372 | 4. Fire, Life Safety & Compliance | Handrail extensions missing | Stairs ↔ Accessibility | Handrails need clear extensions. | Com/Res | New build
373 | 4. Fire, Life Safety & Compliance | Tactile indicators clash with stair nosing | Tactiles ↔ Stairs | Tactile layout must match stair geometry. | Com | New build
374 | 4. Fire, Life Safety & Compliance | Door opening force too high | Doors ↔ Accessibility | Closers and pressure affect usability. | Com | New build
375 | 4. Fire, Life Safety & Compliance | Accessible parking location non-compliant | Parking ↔ Accessible path | Spaces must connect with accessible routes. | Com | New build
376 | 4. Fire, Life Safety & Compliance | Adaptable housing requirements missed | Apartment plan ↔ Accessibility | Plans must allow later adaptation. | Res | New build
377 | 4. Fire, Life Safety & Compliance | Energy efficiency rating fails | Envelope/HVAC ↔ Energy code | Combined systems decide energy rating. | Res/Com | New build
378 | 4. Fire, Life Safety & Compliance | Glazing area exceeds energy limit | Glazing ↔ Energy code | More glass increases heat gain/loss. | Com/Res | New build
379 | 4. Fire, Life Safety & Compliance | Lighting power density too high | Lighting ↔ Energy code | Lighting load is capped per area. | Com | New build
380 | 4. Fire, Life Safety & Compliance | HVAC efficiency below code | HVAC ↔ Energy code | Equipment must meet minimum efficiency. | Com | New build/Refurb
381 | 4. Fire, Life Safety & Compliance | Water efficiency fixtures rating not met | Plumbing fixtures ↔ Water code | Fixtures must meet WELS standards. | Res | New build
382 | 4. Fire, Life Safety & Compliance | Stormwater detention required late | Site drainage ↔ Council rules | Councils limit runoff. | Res/Com | New build
383 | 4. Fire, Life Safety & Compliance | Tree removal not permitted | Landscape ↔ Planning | Protected trees limit the building footprint. | Res/Com | New build
384 | 4. Fire, Life Safety & Compliance | Overlooking neighbours requires redesign | Windows ↔ Planning rules | Privacy rules limit window placement. | Res | New build/Extension
385 | 4. Fire, Life Safety & Compliance | Height limit exceeded by plant | Roof plant ↔ Height limit | Rooftop equipment counts against height. | Com | New build
386 | 4. Fire, Life Safety & Compliance | Setback breached by a built element | Building ↔ Planning setbacks | Small encroachments may need approval. | Res | New build/Extension
387 | 4. Fire, Life Safety & Compliance | DA condition requires design changes after approval | Design ↔ Consent conditions | Conditions modify approved design. | All | New build
388 | 4. Fire, Life Safety & Compliance | Occupation certificate withheld | Completed work ↔ Authority sign-off | Occupation depends on final certification. | All | All
389 | 4. Fire, Life Safety & Compliance | Missing certificates delay final inspection | Documentation ↔ Certifier | Evidence must accompany completed work. | All | All
390 | 4. Fire, Life Safety & Compliance | Product used has no test certificate | Materials ↔ Compliance evidence | Unrated products cannot be proven compliant. | All | All
391 | 4. Fire, Life Safety & Compliance | Noise from mechanical plant exceeds the limit | Plant ↔ Neighbour noise limits | External noise limits constrain plant selection. | Com/Ind | All
392 | 4. Fire, Life Safety & Compliance | Light spill complaints from neighbours | External lighting ↔ Planning conditions | Lighting must control spill. | Com/Ind | All
393 | 4. Fire, Life Safety & Compliance | Outdoor kitchen violates fire setbacks | Outdoor kitchen ↔ Fire rules | Appliances need clearance from structures. | Res | Extension
394 | 4. Fire, Life Safety & Compliance | Carport attached to the house requires fire separation | Carport ↔ Dwelling | Attached structures change fire ratings. | Res | Extension
395 | 4. Fire, Life Safety & Compliance | Unprotected openings within the boundary setback | Windows ↔ Fire separation | Openings near boundaries spread fire. | Res | New build/Extension
396 | 4. Fire, Life Safety & Compliance | Secondary dwelling fire separation | Secondary dwelling ↔ Main dwelling | Separation is needed between dwellings. | Res | Extension
397 | 4. Fire, Life Safety & Compliance | Open plan layout defeats smoke compartmentation | Open plan ↔ Smoke control | Large open spaces need extra smoke measures. | Res | Refurb/Upgrade
398 | 4. Fire, Life Safety & Compliance | Basement bedroom lacks egress window | Basement ↔ Egress | Habitable rooms need escape routes. | Res | Refurb/Upgrade
399 | 4. Fire, Life Safety & Compliance | Roof terrace needs a second exit | Roof terrace ↔ Egress | Occupied roofs need exits. | Res/Com | Refurb/Upgrade
400 | 4. Fire, Life Safety & Compliance | Warehouse exit signs obscured by racking | Racking ↔ Egress signage | Racks block sightlines. | Ind | All
401 | 5. Hydraulics, Drainage & Gas | Low water pressure on upper floors | Hydraulics ↔ Building height | Height consumes pressure so pumps must compensate. | Res/Com | New build
402 | 5. Hydraulics, Drainage & Gas | Sewer connection higher than the building drain | Drainage ↔ Civil levels | Gravity flow needs the site to fall to the sewer. | All | New build/Extension
403 | 5. Hydraulics, Drainage & Gas | Larger stormwater tank required | Drainage ↔ Basement/structure | Water storage needs volume that structure must give up. | Com/Res | New build
404 | 5. Hydraulics, Drainage & Gas | Gas supply short for the hot water load | Gas ↔ Hydraulics | Hot water output depends on fuel supply. | Res/Com | New build/Refurb
405 | 5. Hydraulics, Drainage & Gas | Condensate drain has no fall | HVAC ↔ Hydraulics | Cooling units produce water that the drainage must remove. | Com/Res | New build
406 | 5. Hydraulics, Drainage & Gas | Hot water system fails temperature requirements | Hydraulics ↔ Health safety | Water must stay hot enough to prevent bacterial growth. | Com/Res | New build
407 | 5. Hydraulics, Drainage & Gas | Dissimilar metals corrode pipework | Hydraulics ↔ Materials | Material pairing determines long-term integrity. | All | All
408 | 5. Hydraulics, Drainage & Gas | Floor waste not at the low point | Tiling ↔ Hydraulics | Falls in the finish must lead to the drain. | Res/Com | New build
409 | 5. Hydraulics, Drainage & Gas | Water main connection delayed by the authority | Water supply ↔ Programme | Building supply depends on authority works. | All | New build
410 | 5. Hydraulics, Drainage & Gas | Water meter size undersized for demand | Water supply ↔ Peak demand | Meters limit peak flow. | Com/Res | New build
411 | 5. Hydraulics, Drainage & Gas | Water hammer in pipes | Pipework ↔ Valves | Rapid valve closure shocks pipes. | Com/Ind | All
412 | 5. Hydraulics, Drainage & Gas | Pipe noise in bedroom walls | Pipework ↔ Acoustics | Pipes transmit flow noise through framing. | Res | New build
413 | 5. Hydraulics, Drainage & Gas | Pipe expansion not allowed for | Hot pipes ↔ Structure | Pipes expand when heated and need loops. | Com | New build
414 | 5. Hydraulics, Drainage & Gas | Pipe sleeves through slab misplaced | Pipework ↔ Structure | Sleeves must align with pipe runs. | Com/Res | New build
415 | 5. Hydraulics, Drainage & Gas | Pipe clash with beams in ceiling space | Pipework ↔ Structure | Services thread through limited gaps. | Com | New build
416 | 5. Hydraulics, Drainage & Gas | Stack penetration through the waterproof slab leaks | Plumbing stack ↔ Waterproofing | Penetrations need sealed flanges. | Res/Com | New build
417 | 5. Hydraulics, Drainage & Gas | Vent pipe terminates inside the roof space | Drain vent ↔ Roof | Vents must discharge outside. | Res | New build/Extension
418 | 5. Hydraulics, Drainage & Gas | Sewer odour in bathroom | Drainage ↔ Trap seals | Dry traps allow sewer gases. | Res | All
419 | 5. Hydraulics, Drainage & Gas | Siphoned trap in a high-rise stack | Drainage stack ↔ Venting | Pressure fluctuations empty traps. | Res/Com | New build
420 | 5. Hydraulics, Drainage & Gas | Drain blocked by construction debris | Drainage ↔ Construction | Debris enters open drain lines. | All | New build
421 | 5. Hydraulics, Drainage & Gas | Drain collapse under a slab | Underground drain ↔ Slab | Failed pipes cannot be reached later. | Res/Ind | New build/Refurb
422 | 5. Hydraulics, Drainage & Gas | Sewer pump station sizing change | Sewer pumps ↔ Basement layout | Pumps need wet wells and access. | Com | New build
423 | 5. Hydraulics, Drainage & Gas | Grease trap too small for kitchens | Drainage ↔ Kitchen tenancy | Grease must be intercepted before sewers. | Com | New build/Refurb
424 | 5. Hydraulics, Drainage & Gas | Trade waste approval delayed | Drainage ↔ Water authority | Industrial discharge needs approval. | Ind | New build
425 | 5. Hydraulics, Drainage & Gas | Stormwater pit at the wrong level | Stormwater ↔ Pavement | Pits must receive surface flow. | Ind/Com | New build
426 | 5. Hydraulics, Drainage & Gas | Roof downpipes overload the stormwater | Roof drainage ↔ Site drainage | Roof flow concentrates at few outlets. | All | New build
427 | 5. Hydraulics, Drainage & Gas | Siphonic roof drainage fails priming | Roof drainage ↔ Hydraulic design | Siphonic systems rely on correct sizing. | Com/Ind | New build
428 | 5. Hydraulics, Drainage & Gas | Overflow device missing for sealed roof | Roof ↔ Emergency overflow | Blocked outlets need a relief path. | Com | New build
429 | 5. Hydraulics, Drainage & Gas | Detention tank buoyant in groundwater | Tank ↔ Groundwater | Empty tanks float in a high water table. | Com | New build
430 | 5. Hydraulics, Drainage & Gas | Rainwater tank mandated late | Rainwater tank ↔ Site layout | Tanks need space and plumbing connections. | Res | New build/Extension
431 | 5. Hydraulics, Drainage & Gas | Rainwater pump noise | Pump ↔ Bedrooms | Pumps need isolation from sleeping areas. | Res | New build
432 | 5. Hydraulics, Drainage & Gas | Backflow prevention device missing | Plumbing ↔ Water authority rules | Backflow protects the mains from contamination. | Com/Ind | All
433 | 5. Hydraulics, Drainage & Gas | Backflow device installed in a flood-prone pit | Backflow ↔ Drainage | Pits must stay drained and accessible. | Com | New build
434 | 5. Hydraulics, Drainage & Gas | Water treatment fails to meet standard | Water supply ↔ Process use | Process use may need purified water. | Ind | New build
435 | 5. Hydraulics, Drainage & Gas | Legionella risk in cooling towers | Cooling tower ↔ Water quality | Warm stagnant water grows bacteria. | Com | All
436 | 5. Hydraulics, Drainage & Gas | Dead legs in hot water lines | Hot water ↔ Layout | Unused branches stagnate. | Com/Res | Refurb/Upgrade
437 | 5. Hydraulics, Drainage & Gas | Thermostatic mixing valve missing | Hot water ↔ Scald protection | Safe temperatures need mixing valves. | Res/Com | New build
438 | 5. Hydraulics, Drainage & Gas | Hot water unit location exceeds pipe length | Hot water ↔ Layout | Long runs waste heat and water. | Res | New build
439 | 5. Hydraulics, Drainage & Gas | Heat pump hot water installed with no power | Hot water ↔ Electrical | Heat pumps need dedicated circuits. | Res | New build/Refurb
440 | 5. Hydraulics, Drainage & Gas | Solar hot water roof collectors overshadowed | Solar hot water ↔ Roof design | Collectors need unobstructed sun. | Res | New build
441 | 5. Hydraulics, Drainage & Gas | Gas flue clearance to openings not met | Gas appliance ↔ Window/opening | Flues must discharge away from openings. | Res | New build/Extension
442 | 5. Hydraulics, Drainage & Gas | Gas meter location not permitted | Gas ↔ Site planning | Meters have clearance requirements. | Res | New build
443 | 5. Hydraulics, Drainage & Gas | Gas pipe through a fire-rated wall | Gas ↔ Fire compartment | Gas lines need sealed sleeves. | Com/Res | New build
444 | 5. Hydraulics, Drainage & Gas | Gas leak at test | Gas pipework ↔ Joints | Joints must pass pressure tests. | All | All
445 | 5. Hydraulics, Drainage & Gas | Gas supply ban triggers all-electric redesign | Gas ↔ Electrical | Removing gas increases electrical demand. | Res | New build
446 | 5. Hydraulics, Drainage & Gas | Medical gas pipework fails purity test | Medical gas ↔ Contaminants | Clean pipes are mandatory for medical gas. | Com | New build
447 | 5. Hydraulics, Drainage & Gas | Compressed air lines leak | Process services ↔ Plant | Leaks waste energy. | Ind | All
448 | 5. Hydraulics, Drainage & Gas | Process cooling water supply insufficient | Process services ↔ Water mains | Industrial loads exceed mains capacity. | Ind | New build
449 | 5. Hydraulics, Drainage & Gas | Wastewater pretreatment needed | Process waste ↔ Sewer | Discharge standards limit what can go to sewers. | Ind | New build
450 | 5. Hydraulics, Drainage & Gas | Spill containment not connected to drainage | Bunds ↔ Stormwater | Spills must not reach stormwater. | Ind | New build
451 | 5. Hydraulics, Drainage & Gas | Oil separator undersized | Stormwater ↔ Hardstand use | Separators must treat the runoff from vehicle areas. | Ind/Com | New build
452 | 5. Hydraulics, Drainage & Gas | Underfloor drainage conflicts with reinforcement | Drainage ↔ Slab | Drains placed in slabs weaken sections. | Ind | New build
453 | 5. Hydraulics, Drainage & Gas | Site stormwater connects to the wrong pit | Stormwater ↔ Council network | Connection points are set by authority. | All | New build
454 | 5. Hydraulics, Drainage & Gas | Easement drain discovered under the footprint | Private drain ↔ Neighbour | Shared drains cannot be built over. | Res | Extension
455 | 5. Hydraulics, Drainage & Gas | Existing sewer relocation required | Sewer ↔ New building footprint | Building over sewers needs approval. | Res/Com | Extension/New build
456 | 5. Hydraulics, Drainage & Gas | Old galvanised pipes restrict flow | Existing plumbing ↔ New fixtures | Old pipes clog and restrict flow. | Res | Refurb/Upgrade
457 | 5. Hydraulics, Drainage & Gas | Lead pipes discovered | Existing plumbing ↔ Health | Lead plumbing needs replacing. | Res | Refurb/Upgrade
458 | 5. Hydraulics, Drainage & Gas | Cast iron stack cracked | Old drainage ↔ Building structure | Old stacks leak inside walls. | Res/Com | Refurb/Upgrade
459 | 5. Hydraulics, Drainage & Gas | Hidden leaks found after lining removal | Existing plumbing ↔ Wall linings | Leaks hide until walls open. | Res | Refurb/Upgrade
460 | 5. Hydraulics, Drainage & Gas | New bathroom drains cannot fall on an old slab | Bathroom ↔ Existing floor | Slab level restricts drainage falls. | Res | Refurb/Upgrade
461 | 5. Hydraulics, Drainage & Gas | Fixture upgrade overloads old drainage | New fixtures ↔ Old drains | Greater flows exceed old pipe sizes. | Res/Com | Refurb/Upgrade
462 | 5. Hydraulics, Drainage & Gas | Plumbing relocation needs slab cutting | Plumbing ↔ Existing slab | Cutting slabs requires structural checks. | Com/Res | Refurb/Upgrade
463 | 5. Hydraulics, Drainage & Gas | Water supply isolation for tie-ins disrupts occupants | Existing supply ↔ Occupants | Tie-ins require shutdowns. | Com/Res | Refurb/Upgrade
464 | 5. Hydraulics, Drainage & Gas | Extension plumbing exceeds hot water capacity | New load ↔ Existing hot water unit | Systems were sized for the original house. | Res | Extension
465 | 5. Hydraulics, Drainage & Gas | Septic system undersized for the extension | Septic ↔ Added bedrooms | Septic capacity is based on bedrooms. | Res | Extension
466 | 5. Hydraulics, Drainage & Gas | Septic trench conflicts with the extension footprint | Septic ↔ Site layout | Septic systems need setbacks. | Res | Extension
467 | 5. Hydraulics, Drainage & Gas | Greywater reuse rejected | Greywater ↔ Health rules | Treatment rules restrict reuse. | Res | New build
468 | 5. Hydraulics, Drainage & Gas | Tapware flow rate causes complaint | Fixtures ↔ Pressure | Low-flow fixtures reduce performance. | Res | New build
469 | 5. Hydraulics, Drainage & Gas | Water pressure too high damages fixtures | Mains pressure ↔ Fixtures | Pressure-limiting valves are required. | Res | All
470 | 5. Hydraulics, Drainage & Gas | Fixtures delivered not matching rough-in | Fixtures ↔ Plumbing rough-in | Rough-in dimensions rely on specific products. | Res/Com | New build
471 | 5. Hydraulics, Drainage & Gas | Wall hung toilets need heavier framing | Fixtures ↔ Wall framing | Cisterns require structure to carry weight. | Res/Com | New build
472 | 5. Hydraulics, Drainage & Gas | Concealed cistern access missing | Plumbing ↔ Wall finishes | Equipment needs a maintenance route. | Res/Com | New build
473 | 5. Hydraulics, Drainage & Gas | Hydraulic riser too small for services | Riser ↔ Services | Riser space must hold all services. | Res/Com | New build
474 | 5. Hydraulics, Drainage & Gas | Hydraulic riser lacks fire stopping | Riser ↔ Fire rating | Risers connect floors and spread fire. | Res/Com | New build
475 | 5. Hydraulics, Drainage & Gas | Pipe insulation omitted | Hot pipes ↔ Energy code | Insulation reduces losses. | Com | New build
476 | 5. Hydraulics, Drainage & Gas | Condensation on cold pipes drips | Cold pipes ↔ Ceilings | Cold surfaces condense moisture. | Com | New build
477 | 5. Hydraulics, Drainage & Gas | Frozen pipes in unheated areas | Plumbing ↔ Climate | Frost splits exposed pipes. | Res/Ind | All
478 | 5. Hydraulics, Drainage & Gas | Pressure testing leaks flood the floor | Plumbing ↔ Finishes | Testing after finishes causes damage. | Com/Res | New build
479 | 5. Hydraulics, Drainage & Gas | Sprinkler pipe and hydraulic pipe clash | Fire services ↔ Hydraulics | Shared ceiling space is limited. | Com | New build
480 | 5. Hydraulics, Drainage & Gas | Pump room access too small for equipment | Pumps ↔ Plant room | Equipment must be installed and replaced. | Com | New build
481 | 5. Hydraulics, Drainage & Gas | Pump noise heard throughout the building | Pumps ↔ Structure | Vibration travels through slabs. | Com/Res | New build
482 | 5. Hydraulics, Drainage & Gas | Pressure vessel inspection delayed | Plumbing ↔ Authority | Vessels need certificates before use. | Com/Ind | New build
483 | 5. Hydraulics, Drainage & Gas | Water tank cleaning access missing | Tank ↔ Maintenance | Tanks need hatches and ladders. | Com/Ind | New build
484 | 5. Hydraulics, Drainage & Gas | Roof tank loads exceed the slab capacity | Water tank ↔ Roof structure | Full tanks are heavy. | Com | New build
485 | 5. Hydraulics, Drainage & Gas | Chlorine dosing room ventilation inadequate | Pool plant ↔ Ventilation | Chemicals require ventilation. | Com | New build
486 | 5. Hydraulics, Drainage & Gas | Pool plant room undersized | Pool plant ↔ Layout | Equipment needs clearances. | Res/Com | New build
487 | 5. Hydraulics, Drainage & Gas | Pool pump noise complaints | Pool pump ↔ Neighbours | Plant noise travels across boundaries. | Res | All
488 | 5. Hydraulics, Drainage & Gas | Pool barrier fails the test | Pool fence ↔ Safety rules | Barrier heights and gaps are mandated. | Res | All
489 | 5. Hydraulics, Drainage & Gas | Water meter location blocked by landscaping | Water meter ↔ Landscape | Authority needs meter access. | Res | New build
490 | 5. Hydraulics, Drainage & Gas | Overflow relief gully levels wrong | Drainage ↔ Slab levels | Relief gullies must sit below floor level. | Res | New build
491 | 5. Hydraulics, Drainage & Gas | Sewer back-flow floods the lowest level | Sewer ↔ Basement | Basement fixtures sit below sewer level. | Res/Com | All
492 | 5. Hydraulics, Drainage & Gas | Sump pump fails during a storm | Sump ↔ Electrical | Pumps depend on power during storms. | Res/Com | All
493 | 5. Hydraulics, Drainage & Gas | Cooling water make-up demand exceeds supply | Process cooling ↔ Mains | Evaporation needs makeup. | Com/Ind | New build
494 | 5. Hydraulics, Drainage & Gas | Fire sprinkler tank volume increases footprint | Fire tank ↔ Site | Tanks consume space. | Ind | New build
495 | 5. Hydraulics, Drainage & Gas | Fire tank refill rate inadequate | Fire tank ↔ Mains | Tanks must refill within set time. | Ind | New build
496 | 5. Hydraulics, Drainage & Gas | Septic effluent field fails in wet ground | Septic ↔ Soil | Soil absorption varies seasonally. | Res | New build/Extension
497 | 5. Hydraulics, Drainage & Gas | Rainwater downpipes connected to sewer | Roof drainage ↔ Sewer | Illegal connections overload sewers. | Res | All
498 | 5. Hydraulics, Drainage & Gas | Plumbing vents penetrate fire-rated roof spaces | Plumbing ↔ Fire | Penetrations must be sealed. | Res | New build
499 | 5. Hydraulics, Drainage & Gas | Pipework supports missing and pipes sag | Pipework ↔ Fixings | Sagging pipes lose fall. | Com | New build
500 | 5. Hydraulics, Drainage & Gas | Pressure reducing valve fails and bursts appliances | Plumbing ↔ Appliances | Valves protect equipment. | Res | All
501 | 6. Mechanical, Vertical Transport & Acoustics | Chiller too heavy for the planned crane | HVAC ↔ Lifting/structure | Plant must be lifted and supported within structural limits. | Com/Ind | New build
502 | 6. Mechanical, Vertical Transport & Acoustics | Plant vibration heard in apartments | Mechanical ↔ Structure/acoustics | Structure transmits vibration unless isolated. | Res/Com | New build
503 | 6. Mechanical, Vertical Transport & Acoustics | BMS cannot talk to the chillers | Controls ↔ HVAC | Controls only work if the equipment protocols match. | Com | New build/Refurb
504 | 6. Mechanical, Vertical Transport & Acoustics | Generator exhaust too close to an air intake | Electrical ↔ HVAC | Exhaust and fresh air must stay separate. | Com/Ind | New build
505 | 6. Mechanical, Vertical Transport & Acoustics | Services stack shortens ceiling height | Services ↔ Architecture | Floor-to-floor height is shared by structure, services and finishes. | Com | New build
506 | 6. Mechanical, Vertical Transport & Acoustics | No access panels for valves | Services ↔ Ceilings | Maintainable equipment needs reachable locations. | Com | New build
507 | 6. Mechanical, Vertical Transport & Acoustics | Cable tray overheats with high load | Electrical ↔ Ventilation | Current load generates heat that must be dissipated. | Com/Ind | All
508 | 6. Mechanical, Vertical Transport & Acoustics | Ceiling plenum too shallow for ducts | HVAC ↔ Ceiling height | Duct sizes need depth the ceiling void lacks. | Com | New build/Refurb
509 | 6. Mechanical, Vertical Transport & Acoustics | Duct sizes reduced late and noise increases | Ductwork ↔ Acoustics | Smaller ducts raise air velocity and noise. | Com | New build
510 | 6. Mechanical, Vertical Transport & Acoustics | Duct leakage test fails | Ductwork ↔ Energy performance | Leaks waste conditioned air. | Com | New build
511 | 6. Mechanical, Vertical Transport & Acoustics | Duct insulation omitted | Ductwork ↔ Condensation | Cold ducts sweat without insulation. | Com | New build
512 | 6. Mechanical, Vertical Transport & Acoustics | Duct crosses a fire wall without a damper | Ductwork ↔ Fire compartment | Ducts breach compartmentation. | Com | New build
513 | 6. Mechanical, Vertical Transport & Acoustics | Duct clashes with a sprinkler main | Ductwork ↔ Fire services | Ceiling space is limited. | Com | New build
514 | 6. Mechanical, Vertical Transport & Acoustics | Fresh air intake too close to a car park exhaust | Ventilation ↔ Car park | Exhaust contaminates fresh air. | Com/Res | New build
515 | 6. Mechanical, Vertical Transport & Acoustics | Fresh air rate too low for occupancy | Ventilation ↔ Occupant load | Ventilation is based on people numbers. | Com | Refurb/Upgrade
516 | 6. Mechanical, Vertical Transport & Acoustics | Kitchen exhaust makeup air missing | Exhaust ↔ Supply air | Exhaust needs makeup air to work. | Com | New build/Refurb
517 | 6. Mechanical, Vertical Transport & Acoustics | Range hood exhaust sucks air through flues | Exhaust ↔ Gas appliances | Negative pressure backdrafts flues. | Res | New build
518 | 6. Mechanical, Vertical Transport & Acoustics | Bathroom fan too weak | Exhaust ↔ Moisture | Weak fans leave humidity. | Res | New build
519 | 6. Mechanical, Vertical Transport & Acoustics | Condenser unit location violates noise rules | HVAC ↔ Neighbour noise | Outdoor units must meet noise limits. | Res | New build/Extension
520 | 6. Mechanical, Vertical Transport & Acoustics | Split system line length exceeded | HVAC ↔ Layout | Pipe length affects capacity. | Res | Refurb/Upgrade
521 | 6. Mechanical, Vertical Transport & Acoustics | Refrigerant pipe not insulated | HVAC ↔ Efficiency | Pipes lose capacity. | Res | New build
522 | 6. Mechanical, Vertical Transport & Acoustics | Refrigerant leak detection missing | HVAC ↔ Safety | Refrigerant leaks need alarms in confined spaces. | Com | New build
523 | 6. Mechanical, Vertical Transport & Acoustics | VRF unit capacity insufficient in peak heat | HVAC ↔ Climate | Design conditions underestimate extreme days. | Com/Res | New build
524 | 6. Mechanical, Vertical Transport & Acoustics | Chilled water pipework flushing delayed | HVAC ↔ Programme | Systems must be clean before commissioning. | Com | New build
525 | 6. Mechanical, Vertical Transport & Acoustics | Cooling tower makes plume complaints | HVAC ↔ Neighbours | Plumes cause amenity issues. | Com | New build
526 | 6. Mechanical, Vertical Transport & Acoustics | Rooftop unit access ladder missing | Rooftop plant ↔ Maintenance | Plant needs safe access. | Com/Ind | New build
527 | 6. Mechanical, Vertical Transport & Acoustics | Rooftop plant screening blocks airflow | Plant ↔ Screens | Screens restrict air to condensers. | Com | New build
528 | 6. Mechanical, Vertical Transport & Acoustics | Plant platforms not coordinated with roof drains | Plant ↔ Roof drainage | Platforms obstruct drainage paths. | Com | New build
529 | 6. Mechanical, Vertical Transport & Acoustics | Plant room located under bedrooms | Plant ↔ Acoustics | Noise transmits through floors. | Res | New build
530 | 6. Mechanical, Vertical Transport & Acoustics | Plant room too hot due to no ventilation | Plant ↔ Ventilation | Equipment gives off heat that must be removed. | Com | New build
531 | 6. Mechanical, Vertical Transport & Acoustics | Ductwork support fixings overload slab | Services support ↔ Structure | Hangers add load at points. | Com | New build
532 | 6. Mechanical, Vertical Transport & Acoustics | Services hangers fixed into PT slab | Services ↔ PT tendons | Drilling anchors into PT slabs risks cutting tendons. | Com | New build
533 | 6. Mechanical, Vertical Transport & Acoustics | Tenant fit-out ductwork exceeds base building capacity | Fit-out HVAC ↔ Base building | Base systems have limited spare capacity. | Com | Refurb/Upgrade
534 | 6. Mechanical, Vertical Transport & Acoustics | Tenant requires 24 hour cooling and the base system cannot | Base HVAC ↔ Tenant | Systems are designed for standard hours. | Com | Refurb/Upgrade
535 | 6. Mechanical, Vertical Transport & Acoustics | Server room cooling overloads the building | Data room ↔ HVAC | IT loads are heat dense. | Com | Refurb/Upgrade
536 | 6. Mechanical, Vertical Transport & Acoustics | Heat from a server room not rejected | Data room ↔ Condensers | Heat must go somewhere. | Com | Refurb/Upgrade
537 | 6. Mechanical, Vertical Transport & Acoustics | Warehouse heating inadequate for ceiling height | HVAC ↔ Tall space | Hot air stratifies at height. | Ind | New build
538 | 6. Mechanical, Vertical Transport & Acoustics | Destratification fans omitted | HVAC ↔ Tall volume | Fans help mix air. | Ind | New build
539 | 6. Mechanical, Vertical Transport & Acoustics | Industrial extraction fan noise | Extraction ↔ Neighbours | Exhausts must meet noise limits. | Ind | New build
540 | 6. Mechanical, Vertical Transport & Acoustics | Process exhaust discharge height too low | Exhaust ↔ Environmental rules | Discharge height controls dispersion. | Ind | New build
541 | 6. Mechanical, Vertical Transport & Acoustics | Dust collection system overloads ducting | Process extraction ↔ Ducts | Dust collection needs specific velocities. | Ind | New build
542 | 6. Mechanical, Vertical Transport & Acoustics | Clean room air changes not achieved | HVAC ↔ Clean room | Rooms must meet cleanliness rates. | Ind | New build
543 | 6. Mechanical, Vertical Transport & Acoustics | HVAC commissioning discovers wrong fan rotation | HVAC ↔ Electrical | Phase sequence decides motor direction. | Com | New build
544 | 6. Mechanical, Vertical Transport & Acoustics | Controls sensors placed in poor locations | BMS ↔ Occupied spaces | Sensor location drives control accuracy. | Com | New build
545 | 6. Mechanical, Vertical Transport & Acoustics | Thermostat location unsuitable | Controls ↔ Space layout | Thermostats near heat sources misread. | Res | New build
546 | 6. Mechanical, Vertical Transport & Acoustics | VAV boxes inaccessible | HVAC ↔ Ceilings | Boxes need access for balancing. | Com | New build
547 | 6. Mechanical, Vertical Transport & Acoustics | Air balancing cannot be completed | HVAC ↔ Ductwork | Dampers must be accessible and set. | Com | New build
548 | 6. Mechanical, Vertical Transport & Acoustics | Energy metering missing | HVAC ↔ Energy rating | Rating schemes require sub-meters. | Com | New build
549 | 6. Mechanical, Vertical Transport & Acoustics | Economy cycle (free cooling) not working | HVAC ↔ Controls | Controls decide when to use outside air. | Com | New build
550 | 6. Mechanical, Vertical Transport & Acoustics | Heat recovery unit larger than planned | HVAC ↔ Plant space | Recovery equipment adds size. | Com | New build
551 | 6. Mechanical, Vertical Transport & Acoustics | Mechanical ventilation required for new airtight envelope | Envelope ↔ HVAC | Airtight shells need mechanical ventilation. | Res | New build
552 | 6. Mechanical, Vertical Transport & Acoustics | Mould due to poor ventilation in an extension | Extension ↔ Ventilation | New rooms may lack airflow. | Res | Extension
553 | 6. Mechanical, Vertical Transport & Acoustics | Existing HVAC cannot serve an extension | Existing HVAC ↔ New area | Capacity was set by the original. | Res | Extension
554 | 6. Mechanical, Vertical Transport & Acoustics | Existing ductwork contains asbestos | Old ducts ↔ Hazmat | Old insulation can contain asbestos. | Com | Refurb/Upgrade
555 | 6. Mechanical, Vertical Transport & Acoustics | Refrigerant phase-out forces plant replacement | Old chillers ↔ Regulation | Obsolete refrigerants limit repair. | Com | Refurb/Upgrade
556 | 6. Mechanical, Vertical Transport & Acoustics | Plant replaced and new unit does not fit old space | New plant ↔ Old plant room | Modern units have different dimensions. | Com | Refurb/Upgrade
557 | 6. Mechanical, Vertical Transport & Acoustics | Plant removal route blocked | Plant ↔ Building access | Equipment must go in and come out. | Com | Refurb/Upgrade
558 | 6. Mechanical, Vertical Transport & Acoustics | Lift motor room undersized | Lift ↔ Machine room | Lift suppliers specify room dimensions. | Com/Res | New build
559 | 6. Mechanical, Vertical Transport & Acoustics | Lift overrun exceeds the roof height | Lift ↔ Roof structure | Overruns decide roof levels. | Com/Res | New build
560 | 6. Mechanical, Vertical Transport & Acoustics | Lift installation delayed by builder's work | Lift ↔ Core readiness | Cores must be ready for lift install. | Com/Res | New build
561 | 6. Mechanical, Vertical Transport & Acoustics | Lift used as a construction hoist is damaged | Lift ↔ Site logistics | Using permanent lifts wears them. | Com/Res | New build
562 | 6. Mechanical, Vertical Transport & Acoustics | Lift commissioning fails fire mode | Lift ↔ Fire alarm | Lifts must recall on fire. | Com | New build
563 | 6. Mechanical, Vertical Transport & Acoustics | Lift lobby too small for gurney turn | Lift ↔ Layout | Emergency access needs space. | Com/Res | New build
564 | 6. Mechanical, Vertical Transport & Acoustics | Lift door fire rating missing | Lift ↔ Fire rating | Lift doors form part of the shaft rating. | Com | New build
565 | 6. Mechanical, Vertical Transport & Acoustics | Lift shaft ventilation vent blocked | Lift ↔ Ventilation | Vents relieve smoke and pressure. | Com | New build
566 | 6. Mechanical, Vertical Transport & Acoustics | Lift shaft water ingress | Lift ↔ Waterproofing | Water damages lift equipment. | Com | New build
567 | 6. Mechanical, Vertical Transport & Acoustics | Escalator support deflects | Escalator ↔ Structure | Escalators need stiff supports. | Com | New build
568 | 6. Mechanical, Vertical Transport & Acoustics | Escalator delivery cannot pass through openings | Escalator ↔ Building opening | Long units need temporary openings. | Com | New build
569 | 6. Mechanical, Vertical Transport & Acoustics | Travelator slope not achievable | Travelator ↔ Floor levels | Slope depends on floor-to-floor height. | Com | New build
570 | 6. Mechanical, Vertical Transport & Acoustics | Goods hoist capacity changes | Hoist ↔ Structure | Hoist loads transfer to supports. | Ind | New build
571 | 6. Mechanical, Vertical Transport & Acoustics | Dock leveller installation clash with slab reinforcement | Dock leveller ↔ Slab | Pits conflict with reinforcement. | Ind | New build
572 | 6. Mechanical, Vertical Transport & Acoustics | Overhead crane installation delayed | Crane ↔ Building completion | Crane install needs complete runway and power. | Ind | New build
573 | 6. Mechanical, Vertical Transport & Acoustics | Acoustic rating of floors not achieved | Floors ↔ Impact noise | Floor build-up affects noise transfer. | Res | New build
574 | 6. Mechanical, Vertical Transport & Acoustics | Acoustic rating compromised by recessed downlights | Ceilings ↔ Acoustics | Holes weaken ceiling performance. | Res | New build
575 | 6. Mechanical, Vertical Transport & Acoustics | Acoustic seals missing on doors | Doors ↔ Acoustics | Gaps pass sound. | Com/Res | New build
576 | 6. Mechanical, Vertical Transport & Acoustics | Reverberation too high in the large space | Interior finishes ↔ Acoustics | Hard surfaces reverberate. | Com | New build
577 | 6. Mechanical, Vertical Transport & Acoustics | Speech privacy fails in meeting rooms | Partitions ↔ Ceiling void | Sound flanks through the void. | Com | New build/Refurb
578 | 6. Mechanical, Vertical Transport & Acoustics | Partition does not extend to the slab | Partitions ↔ Acoustics | Partitions to ceiling only leak sound. | Com | New build/Refurb
579 | 6. Mechanical, Vertical Transport & Acoustics | Mechanical noise transmits via ducts | HVAC ↔ Acoustics | Ducts carry fan noise. | Com | New build
580 | 6. Mechanical, Vertical Transport & Acoustics | Footfall noise from timber floors | Floors ↔ Acoustics | Light floors transmit impact. | Res | New build/Refurb
581 | 6. Mechanical, Vertical Transport & Acoustics | Plumbing noise through a floor penetration | Plumbing ↔ Acoustics | Penetrations create acoustic gaps. | Res | New build
582 | 6. Mechanical, Vertical Transport & Acoustics | Lift noise heard in adjacent apartments | Lift ↔ Acoustics | Lift guide rails transmit vibration. | Res | New build
583 | 6. Mechanical, Vertical Transport & Acoustics | Traffic noise exceeds internal limits | Façade ↔ Acoustics | Glass and seals decide internal noise. | Res | New build
584 | 6. Mechanical, Vertical Transport & Acoustics | Acoustic glazing requires mechanical ventilation | Acoustics ↔ HVAC | Sealed windows need mechanical air. | Res | New build
585 | 6. Mechanical, Vertical Transport & Acoustics | Noise from an industrial neighbour affects a new house | Envelope ↔ Acoustics | Planning may require upgraded envelope. | Res | New build
586 | 6. Mechanical, Vertical Transport & Acoustics | Sound masking system interferes with a fire alarm | Audio ↔ Fire system | Audio systems must not mask alarms. | Com | New build
587 | 6. Mechanical, Vertical Transport & Acoustics | PA/voice evacuation intelligibility fails | Audio ↔ Fire system | Evacuation messages must be intelligible. | Com | New build
588 | 6. Mechanical, Vertical Transport & Acoustics | Vibration from a nearby railway affects equipment | Structure ↔ Sensitive equipment | Sensitive equipment needs isolated floors. | Com | New build
589 | 6. Mechanical, Vertical Transport & Acoustics | Floor vibration limits fail for a laboratory | Structure ↔ Lab equipment | Stiff floors are needed. | Com | New build
590 | 6. Mechanical, Vertical Transport & Acoustics | Cleanroom slab flatness | Slab ↔ Equipment | Precision equipment requires flat slabs. | Ind | New build
591 | 6. Mechanical, Vertical Transport & Acoustics | Hospital theatre HVAC pressure cascade fails | HVAC ↔ Clinical rooms | Pressure keeps contaminants out. | Com | New build
592 | 6. Mechanical, Vertical Transport & Acoustics | Isolation room pressure incorrect | HVAC ↔ Infection control | Negative pressure holds contagion. | Com | New build/Refurb
593 | 6. Mechanical, Vertical Transport & Acoustics | Kitchen extraction recirculation not permitted | Exhaust ↔ Regulations | Recirculation may be banned in some uses. | Com | New build
594 | 6. Mechanical, Vertical Transport & Acoustics | Swimming pool hall humidity damages structure | HVAC ↔ Envelope | Humid air attacks materials. | Com | New build
595 | 6. Mechanical, Vertical Transport & Acoustics | Hot roof makes upstairs rooms uncomfortably warm | Roof ↔ Insulation/HVAC | Heat gain drives cooling load. | Res | All
596 | 6. Mechanical, Vertical Transport & Acoustics | Solar gains cause overheating in apartments | Glazing ↔ HVAC | Large glass areas increase cooling load. | Res | New build
597 | 6. Mechanical, Vertical Transport & Acoustics | Ceiling fans interfere with sprinkler operation | Fans ↔ Fire sprinklers | Airflow can delay sprinkler activation. | Com | New build
598 | 6. Mechanical, Vertical Transport & Acoustics | Ceiling-mounted unit weight needs extra slab fixings | HVAC ↔ Slab | Unit weight must reach structure. | Com | New build
599 | 6. Mechanical, Vertical Transport & Acoustics | Roof penetrations for ducts leak | HVAC ↔ Roofing | Duct penetrations must be flashed. | Com/Ind | All
600 | 6. Mechanical, Vertical Transport & Acoustics | Heat pump outdoor units need acoustic enclosures | HVAC ↔ Neighbours | Noise limits drive enclosures. | Res | New build/Extension
601 | 7. Electrical, Communications & Controls | Switchboard room too small | Electrical ↔ Architecture | Equipment needs working clearances that planning must reserve. | Com/Res | New build
602 | 7. Electrical, Communications & Controls | Utility delays transformer connection | Electrical ↔ Utility network | The building's power depends on an external network. | Com/Ind | New build
603 | 7. Electrical, Communications & Controls | Lightning protection path blocked | Electrical ↔ Structure/façade | The earth path must be continuous through the building. | Com/Ind | New build
604 | 7. Electrical, Communications & Controls | Solar array exceeds roof capacity | PV ↔ Roof structure | Roof loads and penetrations must accommodate added equipment. | Com/Res | All
605 | 7. Electrical, Communications & Controls | Comms riser clashes with the hydraulic stack | Data ↔ Hydraulics | Vertical risers compete for the same shaft space. | Com/Res | New build
606 | 7. Electrical, Communications & Controls | Substation location not approved | Electrical supply ↔ Site layout | Utility requirements fix substation locations. | Com/Ind | New build
607 | 7. Electrical, Communications & Controls | Substation noise and EMF complaints | Substation ↔ Neighbours | Equipment must be set back from sensitive uses. | Com | New build
608 | 7. Electrical, Communications & Controls | Transformer room ventilation inadequate | Transformer ↔ HVAC | Transformers generate heat. | Com/Ind | New build
609 | 7. Electrical, Communications & Controls | Transformer delivery lead time 12 months | Electrical supply ↔ Programme | Long-lead equipment drives energisation date. | Com/Ind | New build
610 | 7. Electrical, Communications & Controls | Power supply capacity less than the load | Electrical ↔ Network capacity | Utility may require upgrades. | Ind/Com | New build/Refurb
611 | 7. Electrical, Communications & Controls | Generator fuel storage fails the fire code | Generator ↔ Fire safety | Fuel is a fire and spill risk. | Com | New build
612 | 7. Electrical, Communications & Controls | Generator load bank test fails | Generator ↔ Electrical | Real load reveals performance limits. | Com | New build
613 | 7. Electrical, Communications & Controls | Generator exhaust causes smoke complaints | Generator ↔ Neighbours | Exhaust discharge needs height. | Com | New build
614 | 7. Electrical, Communications & Controls | Automatic transfer switch fails | Standby power ↔ Controls | Transfer must happen on mains failure. | Com | New build
615 | 7. Electrical, Communications & Controls | UPS room battery ventilation missing | UPS ↔ Ventilation | Batteries release gases. | Com | New build
616 | 7. Electrical, Communications & Controls | Battery storage fire risk | Battery systems ↔ Fire safety | Lithium batteries need separation and detection. | Res/Com | New build/Refurb
617 | 7. Electrical, Communications & Controls | EV charging load exceeds the supply | EV charging ↔ Electrical capacity | Charging adds large demand. | Res/Com | New build/Refurb
618 | 7. Electrical, Communications & Controls | EV charger location needs conduits post-slab | EV charging ↔ Car park | Retrofitting conduits is expensive. | Res/Com | Refurb/Upgrade
619 | 7. Electrical, Communications & Controls | Main switchboard shop drawings not approved | Electrical ↔ Procurement | Boards have long lead times. | Com | New build
620 | 7. Electrical, Communications & Controls | Switchboard arrives damaged | Switchboard ↔ Logistics | Boards need protected transport. | Com | New build
621 | 7. Electrical, Communications & Controls | Cable route clashes with services | Cable trays ↔ Other services | Trays need clear routes. | Com | New build
622 | 7. Electrical, Communications & Controls | Cable pulled around tight bends damaged | Cables ↔ Containment | Bend radius protects cables. | Com/Ind | New build
623 | 7. Electrical, Communications & Controls | Cable sizing changed for voltage drop | Cables ↔ Containment | Larger cables need larger trays. | Com/Ind | New build
624 | 7. Electrical, Communications & Controls | Cable tray earthing discontinuous | Containment ↔ Earthing | Earth continuity ensures safety. | Com | New build
625 | 7. Electrical, Communications & Controls | Conduits not installed before slab pour | Electrical ↔ Slab | Slab conduits cannot be added later. | Res | New build
626 | 7. Electrical, Communications & Controls | Conduit clashes with rebar | Electrical ↔ Reinforcement | Conduits weaken or displace steel. | Com | New build
627 | 7. Electrical, Communications & Controls | Switchboard installed in a wet area | Electrical ↔ Waterproofing | Water ingress causes failures. | Res | New build
628 | 7. Electrical, Communications & Controls | Circuit breakers trip under start-up loads | Electrical ↔ HVAC | Motors have high inrush currents. | Com/Ind | New build
629 | 7. Electrical, Communications & Controls | Earth fault loop impedance too high | Electrical ↔ Protection | Earth path decides protection performance. | Com | New build
630 | 7. Electrical, Communications & Controls | Residual current device nuisance trips | Electrical ↔ Wet areas | Moisture creates leakage. | Res | All
631 | 7. Electrical, Communications & Controls | Phase imbalance in the building | Electrical ↔ Load layout | Unbalanced loads cause overheating. | Com | New build
632 | 7. Electrical, Communications & Controls | Harmonics from drives disturb systems | Electrical ↔ Variable speed drives | Drives distort supply. | Ind/Com | New build
633 | 7. Electrical, Communications & Controls | Lighting dimmers incompatible with LEDs | Lighting ↔ Controls | Controls must match fittings. | Res/Com | New build
634 | 7. Electrical, Communications & Controls | Light fittings delivered with the wrong colour temperature | Lighting ↔ Design intent | Colour shifts the character of space. | Res/Com | New build
635 | 7. Electrical, Communications & Controls | Light fittings cannot fit ceiling void | Lighting ↔ Ceiling depth | Fittings need depth for drivers. | Res/Com | New build
636 | 7. Electrical, Communications & Controls | Downlights clash with insulation | Lighting ↔ Insulation | Insulation near fittings overheats them. | Res | New build/Refurb
637 | 7. Electrical, Communications & Controls | Emergency lighting batteries fail | Emergency lighting ↔ Testing | Batteries must last the rated period. | Com | New build
638 | 7. Electrical, Communications & Controls | Daylight sensor controls misbehave | Lighting ↔ Controls | Sensors depend on calibration. | Com | New build
639 | 7. Electrical, Communications & Controls | Lighting control system integration fails | Lighting controls ↔ BMS | Systems must communicate. | Com | New build
640 | 7. Electrical, Communications & Controls | Lighting levels fail the code | Lighting ↔ Visual comfort | Spaces need minimum lux. | Com/Ind | New build
641 | 7. Electrical, Communications & Controls | High-bay lighting inaccessible for maintenance | Lighting ↔ Operations | Maintenance needs lifts or platforms. | Ind | New build
642 | 7. Electrical, Communications & Controls | Sports lighting spill complaints | Lighting ↔ Neighbours | Spill is limited by planning. | Com | New build
643 | 7. Electrical, Communications & Controls | Façade lighting power not provided | Lighting ↔ Façade | Feature lighting needs circuits at the façade. | Com | New build
644 | 7. Electrical, Communications & Controls | Smart home system incompatible with wiring | Smart controls ↔ Cabling | Systems need dedicated cabling. | Res | New build/Refurb
645 | 7. Electrical, Communications & Controls | Data cabling run exceeds the distance limit | Data ↔ Layout | Cable lengths are limited by standards. | Com | New build
646 | 7. Electrical, Communications & Controls | Data riser cable fire stopping missing | Data ↔ Fire rating | Cable risers breach compartment ratings. | Com | New build
647 | 7. Electrical, Communications & Controls | Wi-Fi coverage poor in steel buildings | Data ↔ Structure | Steel and concrete block signals. | Com/Ind | New build
648 | 7. Electrical, Communications & Controls | Mobile coverage poor inside a high-performance façade | Data ↔ Glazing | Coatings block signals. | Com | New build
649 | 7. Electrical, Communications & Controls | In-building coverage system required | Data ↔ Emergency services | Emergency radio coverage may be mandated. | Com | New build
650 | 7. Electrical, Communications & Controls | NBN or telecom pit position conflicts with the footprint | Telecom ↔ Site layout | Authority pits fix connection points. | Res | New build/Extension
651 | 7. Electrical, Communications & Controls | Fibre conduit not installed to the boundary | Telecom ↔ Site | Late conduits require trenching. | Res/Com | New build
652 | 7. Electrical, Communications & Controls | Telecom cabinet location rejected | Telecom ↔ Streetscape | Cabinets have planning limits. | Res | New build
653 | 7. Electrical, Communications & Controls | Security system cabling not coordinated | Security ↔ Electrical | Cabling must be planned early. | Com | New build
654 | 7. Electrical, Communications & Controls | Access control readers on glass doors | Security ↔ Glazing | Fixings in glass need design. | Com | New build
655 | 7. Electrical, Communications & Controls | Door hardware incompatible with access control | Security ↔ Doors | Locks must match readers. | Com | New build
656 | 7. Electrical, Communications & Controls | CCTV cameras cannot see due to columns | Security ↔ Structure | Layout must consider sightlines. | Com | New build
657 | 7. Electrical, Communications & Controls | Intercom system for apartments incompatible | Security ↔ Apartments | Systems need riser capacity. | Res | New build
658 | 7. Electrical, Communications & Controls | Fire alarm and security systems conflict on lock release | Security ↔ Fire | Doors must release on alarm. | Com | New build
659 | 7. Electrical, Communications & Controls | Automatic doors fail to unlock on power loss | Doors ↔ Electrical | Fail-safe design is required. | Com | New build
660 | 7. Electrical, Communications & Controls | Door controller power supplies in the wrong location | Doors ↔ Electrical | Controllers need power at doors. | Com | New build
661 | 7. Electrical, Communications & Controls | Automatic gate controls conflict with emergency access | Gates ↔ Fire access | Brigade requires access. | Res/Com | New build
662 | 7. Electrical, Communications & Controls | Boom gate loops cut by pavement saw | Parking ↔ Civil | Sensors in pavement must be located precisely. | Com | New build
663 | 7. Electrical, Communications & Controls | Car park lighting trips on a sensor fault | Lighting ↔ Controls | Controls determine safety lighting. | Com | New build
664 | 7. Electrical, Communications & Controls | BMS programming incomplete at handover | BMS ↔ Commissioning | Controls complete the system operation. | Com | New build
665 | 7. Electrical, Communications & Controls | BMS graphics do not match the installed system | BMS ↔ Documentation | Operators rely on accurate graphics. | Com | New build
666 | 7. Electrical, Communications & Controls | Cybersecurity requirement for BMS | BMS ↔ IT policy | Networked systems must be secured. | Com | New build
667 | 7. Electrical, Communications & Controls | Metering system misreports | Metering ↔ Billing | Meters decide tenant cost recovery. | Com | New build
668 | 7. Electrical, Communications & Controls | Solar inverter location overheats | PV ↔ Ventilation | Inverters need cool, ventilated places. | Res/Com | New build
669 | 7. Electrical, Communications & Controls | Solar panels shaded by a neighbouring building | PV ↔ Site context | Shading cuts output. | Res | New build
670 | 7. Electrical, Communications & Controls | Solar panel fixings leak the roof | PV ↔ Roofing | Fixings penetrate the weatherproof layer. | Res | New build/Retrofit
671 | 7. Electrical, Communications & Controls | Solar panels not installed on roof frames | PV ↔ Roof structure | Panels need structural support. | Res/Com | Refurb/Upgrade
672 | 7. Electrical, Communications & Controls | Solar design not allowed for fire fighter access | PV ↔ Fire safety | Roof access paths are required. | Res/Com | New build
673 | 7. Electrical, Communications & Controls | Grid connection restricted export | PV ↔ Network | Utility limits solar export. | Com | New build
674 | 7. Electrical, Communications & Controls | Power factor correction needed | Electrical ↔ Utility | Utility penalises poor power factor. | Ind | New build
675 | 7. Electrical, Communications & Controls | Load shedding controls omitted | Electrical ↔ Peak demand | Controls reduce peak charges. | Com | New build
676 | 7. Electrical, Communications & Controls | Existing wiring unsafe on inspection | Existing electrical ↔ Compliance | Old wiring needs replacement. | Res | Refurb/Upgrade
677 | 7. Electrical, Communications & Controls | Aluminium wiring found | Old wiring ↔ Safety | Old aluminium wiring needs special handling. | Res | Refurb/Upgrade
678 | 7. Electrical, Communications & Controls | Old switchboard contains asbestos | Old switchboards ↔ Hazmat | Boards may contain asbestos. | Res/Ind | Refurb/Upgrade
679 | 7. Electrical, Communications & Controls | Single phase supply cannot support the extension | Existing supply ↔ New load | Larger loads need three phase. | Res | Extension
680 | 7. Electrical, Communications & Controls | Meter box relocation required | Meter ↔ Extension | Extensions can block meter access. | Res | Extension
681 | 7. Electrical, Communications & Controls | Overhead power lines clash with the second storey | Overhead lines ↔ Extension | Clearance to lines is mandatory. | Res | Extension
682 | 7. Electrical, Communications & Controls | Underground cable found during excavation | Cables ↔ Excavation | Live cables are a life safety risk. | All | All
683 | 7. Electrical, Communications & Controls | Electrical isolation for a refurb disrupts occupants | Existing electrical ↔ Occupants | Isolations require outages. | Com | Refurb/Upgrade
684 | 7. Electrical, Communications & Controls | Tenant fit-out exceeds the electrical rising main capacity | Rising main ↔ Tenant load | Mains were sized for typical loads. | Com | Refurb/Upgrade
685 | 7. Electrical, Communications & Controls | Lack of spare conduit capacity | Electrical ↔ Existing containment | Existing risers are full. | Com | Refurb/Upgrade
686 | 7. Electrical, Communications & Controls | Fire alarm replacement needs a building shutdown | Fire alarm ↔ Occupancy | Alarm systems must stay active during use. | Com | Refurb/Upgrade
687 | 7. Electrical, Communications & Controls | Old lighting controls cannot dim LED | Controls ↔ LED | Legacy dimmers are incompatible. | Com | Refurb/Upgrade
688 | 7. Electrical, Communications & Controls | Emergency lighting layout changes with new partitions | Emergency lighting ↔ Layout | Layout change alters coverage. | Com | Refurb/Upgrade
689 | 7. Electrical, Communications & Controls | Intrusion into ceilings reveals hidden hazards | Ceiling cavity ↔ Existing services | Old cavities have unrecorded cables and asbestos. | Com | Refurb/Upgrade
690 | 7. Electrical, Communications & Controls | Electrical testing finds insulation resistance low | Cables ↔ Moisture | Wet cables fail testing. | Com | New build
691 | 7. Electrical, Communications & Controls | Thermal imaging finds hot joints | Switchboard ↔ Terminations | Loose terminations overheat. | Com | New build
692 | 7. Electrical, Communications & Controls | Power quality problems on a sensitive process | Electrical ↔ Process equipment | Sensitive equipment needs clean power. | Ind | New build
693 | 7. Electrical, Communications & Controls | Electromagnetic interference in medical suite | Electrical ↔ Medical equipment | Equipment needs shielding. | Com | New build
694 | 7. Electrical, Communications & Controls | Smart meter installation delayed | Electrical ↔ Retailer | Energisation waits for metering. | Res | New build
695 | 7. Electrical, Communications & Controls | Main earth stake cannot be driven in rock | Earthing ↔ Ground | Earthing relies on soil. | Res/Com | New build
696 | 7. Electrical, Communications & Controls | Underground power conduit crushed by compaction | Electrical conduit ↔ Earthworks | Heavy compactors damage shallow conduits. | All | New build
697 | 7. Electrical, Communications & Controls | Temporary lighting causes a site fire | Temporary electrical ↔ Site safety | Temporary power is poorly protected. | All | All
698 | 7. Electrical, Communications & Controls | Lightning surge damages controls | Electrical ↔ Controls | Surge protection protects electronics. | Com/Ind | All
699 | 7. Electrical, Communications & Controls | Cable penetrations through the roof leak | Electrical ↔ Roofing | Penetrations must be sealed. | Res/Com | All
700 | 7. Electrical, Communications & Controls | Cabling inaccessible after plaster | Electrical ↔ Linings | Concealed cables cannot be repaired. | Res | New build
701 | 8. Finishes, Joinery & Fit-out | Timber floor cups | Flooring ↔ Slab moisture | Finishes react to moisture from the structure beneath. | Res/Com | New build/Refurb
702 | 8. Finishes, Joinery & Fit-out | Tiles crack over a slab joint | Tiling ↔ Structural movement | Rigid finishes cannot absorb substrate movement. | Res/Com | New build
703 | 8. Finishes, Joinery & Fit-out | Paint blisters | Paint ↔ Substrate humidity | Coatings need dry stable substrates. | All | All
704 | 8. Finishes, Joinery & Fit-out | Plasterboard cracks | Lining ↔ Frame movement | Linings follow the framing and the framing follows the structure. | Res/Com | New build
705 | 8. Finishes, Joinery & Fit-out | Joinery does not fit | Joinery ↔ Walls | Joinery is made to measure but walls are not built perfect. | Res/Com | New build/Refurb
706 | 8. Finishes, Joinery & Fit-out | Door swing clashes with the fit-out | Doors ↔ Layout/egress | Door clearances are set by use and exit. | Com | Refurb/Upgrade
707 | 8. Finishes, Joinery & Fit-out | Light fittings clash with the sprinkler layout | Lighting ↔ Fire services | Ceiling space is shared between competing devices. | Com | New build
708 | 8. Finishes, Joinery & Fit-out | Carpet adhesive fails | Floor finish ↔ Slab moisture | Adhesives depend on curing and moisture levels. | Com/Res | New build
709 | 8. Finishes, Joinery & Fit-out | Acoustic ceiling interrupted by services | Ceilings ↔ Acoustics/services | A continuous acoustic layer breaks wherever services pass through. | Com | New build
710 | 8. Finishes, Joinery & Fit-out | Floor screed cracks | Screed ↔ Slab | Screeds crack when bonded to moving slabs. | Res/Com | New build
711 | 8. Finishes, Joinery & Fit-out | Floor leveller too thick and cracks | Screed ↔ Substrate | Self-levelling compounds have thickness limits. | Res/Com | Refurb/Upgrade
712 | 8. Finishes, Joinery & Fit-out | Slab moisture reading too high to lay flooring | Slab ↔ Flooring programme | Floors cannot be laid until slabs dry. | Res/Com | New build
713 | 8. Finishes, Joinery & Fit-out | Underfloor heating not commissioned before flooring | Underfloor heating ↔ Flooring | Heating must stabilise before finishes. | Res | New build
714 | 8. Finishes, Joinery & Fit-out | Hydronic heating pipes damaged by tile fixings | Heating ↔ Tiling | Fixings strike embedded pipes. | Res | New build
715 | 8. Finishes, Joinery & Fit-out | Tile pattern needs more setting out than planned | Tiling ↔ Wall layout | Tile size drives layout. | Res/Com | New build
716 | 8. Finishes, Joinery & Fit-out | Large format tiles lippage | Tiling ↔ Substrate flatness | Large tiles need very flat bases. | Res/Com | New build
717 | 8. Finishes, Joinery & Fit-out | Tile colour batch mismatch | Tiles ↔ Appearance | Batch variation appears on large areas. | Res/Com | New build
718 | 8. Finishes, Joinery & Fit-out | Tile adhesive incompatible with the substrate | Tile adhesive ↔ Substrate | Adhesive must bond to the surface. | Res/Com | New build
719 | 8. Finishes, Joinery & Fit-out | Grout stains from cleaning | Grout ↔ Maintenance | Porous grout absorbs contaminants. | Res | All
720 | 8. Finishes, Joinery & Fit-out | Wet area tile trims clash with the waterproofing | Tiling ↔ Waterproofing | Trims fix over membranes. | Res | New build
721 | 8. Finishes, Joinery & Fit-out | Stone floor staining | Stone ↔ Sealers | Unsealed stone stains. | Res/Com | New build
722 | 8. Finishes, Joinery & Fit-out | Polished concrete floor shows cracks | Concrete floor ↔ Finish | Polished slabs reveal flaws. | Com/Ind | New build
723 | 8. Finishes, Joinery & Fit-out | Epoxy floor coating peels | Floor coating ↔ Slab moisture | Moisture breaks the bond. | Ind | New build
724 | 8. Finishes, Joinery & Fit-out | Epoxy floor coating cannot cure in cold | Coating ↔ Temperature | Coatings need specific temperatures. | Ind | New build
725 | 8. Finishes, Joinery & Fit-out | Vinyl flooring telegraphs slab defects | Vinyl ↔ Substrate | Thin finishes show every imperfection. | Com | New build
726 | 8. Finishes, Joinery & Fit-out | Raised access floor height conflicts with doors | Raised floor ↔ Door thresholds | Raised floors change transitions. | Com | Refurb/Upgrade
727 | 8. Finishes, Joinery & Fit-out | Carpet tile colour dye lots vary | Carpet ↔ Appearance | Dye lots vary. | Com | New build
728 | 8. Finishes, Joinery & Fit-out | Carpet joins visible at doorways | Carpet ↔ Layout | Joins show where rolls end. | Com | New build
729 | 8. Finishes, Joinery & Fit-out | Skirting heights differ across rooms | Skirtings ↔ Floor levels | Level changes alter skirting. | Res | New build
730 | 8. Finishes, Joinery & Fit-out | Floor levels differ between rooms | Floor structure ↔ Finishes | Different thicknesses create steps. | Res | New build/Refurb
731 | 8. Finishes, Joinery & Fit-out | Threshold transitions create trip hazards | Floor finishes ↔ Safety | Differing materials need flush transitions. | Com | New build
732 | 8. Finishes, Joinery & Fit-out | Plasterboard sheet joints show in raking light | Plaster ↔ Lighting | Light reveals imperfections. | Com/Res | New build
733 | 8. Finishes, Joinery & Fit-out | Plaster set coat cracks from heat | Plaster ↔ Weather | Rapid drying cracks plaster. | Res | New build
734 | 8. Finishes, Joinery & Fit-out | Plaster dust enters the HVAC | Plastering ↔ Ductwork | Dust contaminates air systems. | Com | New build
735 | 8. Finishes, Joinery & Fit-out | Wet plaster damages installed flooring | Plastering ↔ Flooring | Trade sequence must protect finishes. | Res | New build
736 | 8. Finishes, Joinery & Fit-out | Cornice joints open as the building dries | Cornice ↔ Framing | Drying shrinkage opens joints. | Res | New build
737 | 8. Finishes, Joinery & Fit-out | Paint finish quality fails inspection | Paint ↔ Preparation | Preparation decides finish quality. | Res/Com | New build
738 | 8. Finishes, Joinery & Fit-out | Paint applied before the building is dry | Paint ↔ Moisture | Damp walls cause peeling. | Res | New build
739 | 8. Finishes, Joinery & Fit-out | Paint spec changed to low-VOC causing poor coverage | Paint ↔ Appearance | Different formulations perform differently. | Com | New build
740 | 8. Finishes, Joinery & Fit-out | Wallpaper fails on damp walls | Wallpaper ↔ Moisture | Humid walls lift paper. | Res | Refurb/Upgrade
741 | 8. Finishes, Joinery & Fit-out | Colour selection changed late | Finishes ↔ Procurement | Late changes delay ordering. | Res | New build
742 | 8. Finishes, Joinery & Fit-out | Joinery shop drawings do not match site dimensions | Joinery ↔ Site measure | Joinery fits only if measured accurately. | Res/Com | New build/Refurb
743 | 8. Finishes, Joinery & Fit-out | Joinery delivered before the building is dry | Joinery ↔ Moisture | Moisture swells timber and board. | Res | New build
744 | 8. Finishes, Joinery & Fit-out | Kitchen appliances do not fit cavity | Joinery ↔ Appliances | Appliance dimensions must match. | Res | New build
745 | 8. Finishes, Joinery & Fit-out | Kitchen benchtop sink cut-out wrong | Joinery ↔ Plumbing | Sink dimensions determine the cutout. | Res | New build
746 | 8. Finishes, Joinery & Fit-out | Stone benchtop cracks during installation | Joinery ↔ Stone | Stone is fragile at cutouts. | Res | New build
747 | 8. Finishes, Joinery & Fit-out | Benchtop joins visible | Stone ↔ Layout | Slab sizes force joins. | Res | New build
748 | 8. Finishes, Joinery & Fit-out | Splashback does not align with outlets | Tiling ↔ Electrical | Outlets must align with tile layout. | Res | New build
749 | 8. Finishes, Joinery & Fit-out | Power outlets in the wrong location for joinery | Electrical ↔ Joinery | Outlet positions are coordinated with joinery. | Res | New build
750 | 8. Finishes, Joinery & Fit-out | Cabinet hinge clashes with a wall light | Joinery ↔ Lighting | Layout must consider swing. | Res | New build
751 | 8. Finishes, Joinery & Fit-out | Wardrobe doors hit window architraves | Joinery ↔ Windows | Clearance is needed. | Res | New build
752 | 8. Finishes, Joinery & Fit-out | Stair balustrade out of tolerance | Stairs ↔ Balustrades | Handrails need exact heights. | Res | New build
753 | 8. Finishes, Joinery & Fit-out | Stair tread nosing slippery | Stairs ↔ Finishes | Finish selection affects slip resistance. | Com | New build
754 | 8. Finishes, Joinery & Fit-out | Glass balustrade shatters at install | Glass ↔ Handling | Toughened glass can fail on edges. | Res/Com | New build
755 | 8. Finishes, Joinery & Fit-out | Metalwork fabrication differs from the drawing | Metalwork ↔ Site | Hand fabricated items vary. | Res/Com | New build
756 | 8. Finishes, Joinery & Fit-out | Door hardware delivered the wrong handing | Doors ↔ Hardware | Handing errors need replacement. | Com/Res | New build
757 | 8. Finishes, Joinery & Fit-out | Door frames not square | Door frames ↔ Wall framing | Out-of-square frames cause binding. | Res/Com | New build
758 | 8. Finishes, Joinery & Fit-out | Doors swell and stick | Doors ↔ Humidity | Timber doors absorb moisture. | Res | All
759 | 8. Finishes, Joinery & Fit-out | Door leaf height exceeds opening after floor finish added | Doors ↔ Floor finish | Floor build-up reduces clearance. | Res/Com | New build
760 | 8. Finishes, Joinery & Fit-out | Fire door hardware not compliant | Doors ↔ Fire compliance | Hardware must be rated for the door. | Com | New build
761 | 8. Finishes, Joinery & Fit-out | Door closers too strong for accessibility | Doors ↔ Accessibility | Closers must meet opening force limits. | Com | New build
762 | 8. Finishes, Joinery & Fit-out | Glazed screens deflect | Glass screens ↔ Structure | Framing must be stiff. | Com | New build
763 | 8. Finishes, Joinery & Fit-out | Ceiling tile grid sags | Ceiling ↔ Hangers | Weight and fixings decide sag. | Com | New build
764 | 8. Finishes, Joinery & Fit-out | Ceiling access panels visible | Ceilings ↔ Services | Panels need to blend in. | Com | New build
765 | 8. Finishes, Joinery & Fit-out | Bulkheads hide services but reduce headroom | Bulkheads ↔ Services | Boxing services reduces ceiling height. | Res | New build/Refurb
766 | 8. Finishes, Joinery & Fit-out | Ceiling height below code at a bulkhead | Bulkheads ↔ Regulation | Minimum heights are mandated. | Res | New build/Refurb
767 | 8. Finishes, Joinery & Fit-out | Walls out of plumb disrupt cabinets | Walls ↔ Joinery | Tolerance affects fit. | Res | New build
768 | 8. Finishes, Joinery & Fit-out | Wall chasing for services weakens masonry | Walls ↔ Services | Chases reduce wall capacity. | Res | Refurb/Upgrade
769 | 8. Finishes, Joinery & Fit-out | Wall linings installed before inspection of services | Linings ↔ Inspection | Concealment prevents checks. | All | New build
770 | 8. Finishes, Joinery & Fit-out | Services inspected after linings requiring removal | Inspections ↔ Programme | Missed inspections cause rework. | All | New build
771 | 8. Finishes, Joinery & Fit-out | Fit-out starts before the base building is completed | Fit-out ↔ Base building | Trades clash and damage work. | Com | New build
772 | 8. Finishes, Joinery & Fit-out | Tenant fit-out changes after approval | Fit-out ↔ Base services | Changes affect services and fire. | Com | Refurb/Upgrade
773 | 8. Finishes, Joinery & Fit-out | Retail fit-out signage lacks structure | Signage ↔ Façade | Heavy signs need fixings. | Com | Refurb/Upgrade
774 | 8. Finishes, Joinery & Fit-out | Retail shopfront needs fire separation | Shopfront ↔ Fire | Tenancies must be separated. | Com | Refurb/Upgrade
775 | 8. Finishes, Joinery & Fit-out | Food premises finish requirements not met | Finishes ↔ Health rules | Surfaces must be cleanable. | Com | New build/Refurb
776 | 8. Finishes, Joinery & Fit-out | Commercial kitchen floor falls to drains missing | Kitchen floor ↔ Drainage | Floors must drain. | Com | New build/Refurb
777 | 8. Finishes, Joinery & Fit-out | Cool room floor insulation omitted | Cool room ↔ Slab | Insulation prevents frost heave. | Com/Ind | New build
778 | 8. Finishes, Joinery & Fit-out | Cool room panels do not fit | Cool room ↔ Building dimensions | Panels have standard sizes. | Com/Ind | New build
779 | 8. Finishes, Joinery & Fit-out | Laboratory benches heavier than the floor allows | Lab fit-out ↔ Floor | Loads exceed original design. | Com | Refurb/Upgrade
780 | 8. Finishes, Joinery & Fit-out | Medical equipment shielding omitted | Medical fit-out ↔ Walls | X-ray rooms need lead lining. | Com | New build/Refurb
781 | 8. Finishes, Joinery & Fit-out | Operating theatre ceiling cannot support booms | Medical ↔ Structure | Boom loads need structure. | Com | New build/Refurb
782 | 8. Finishes, Joinery & Fit-out | Loading dock canopy conflicts with fire access | Canopy ↔ Fire | Canopies obstruct access paths. | Ind | New build
783 | 8. Finishes, Joinery & Fit-out | Industrial office mezzanine acoustics poor | Offices ↔ Factory noise | Offices need acoustic separation. | Ind | New build
784 | 8. Finishes, Joinery & Fit-out | Cold storage vapour barrier damaged | Cold store ↔ Envelope | Moisture ingress causes ice. | Ind | New build
785 | 8. Finishes, Joinery & Fit-out | Floor drains in food plants clog | Floor drainage ↔ Hygiene | Drains need cleaning access. | Ind | New build
786 | 8. Finishes, Joinery & Fit-out | Hygienic wall panels do not seal at floors | Wall panels ↔ Floors | Junctions must be coved. | Ind | New build
787 | 8. Finishes, Joinery & Fit-out | Wall corner protection omitted | Walls ↔ Operations | Traffic damages walls. | Ind/Com | All
788 | 8. Finishes, Joinery & Fit-out | Bollards not installed at plant corners | Equipment ↔ Vehicle impacts | Plant needs protection. | Ind | All
789 | 8. Finishes, Joinery & Fit-out | Furniture delivered before cleaning | FF&E ↔ Builder's clean | Dust damages furniture. | Com | New build
790 | 8. Finishes, Joinery & Fit-out | Signage lacks accessible contrast | Signage ↔ Accessibility | Signs must meet contrast and braille rules. | Com | New build
791 | 8. Finishes, Joinery & Fit-out | Artwork or feature wall lacks structural support | Feature items ↔ Structure | Heavy features need backing. | Com | New build
792 | 8. Finishes, Joinery & Fit-out | Window furnishings clash with sprinkler heads | Curtains ↔ Fire | Curtains block coverage. | Com | New build
793 | 8. Finishes, Joinery & Fit-out | Blinds cannot fit due to window design | Window furnishings ↔ Windows | Reveals must allow fit. | Res | New build
794 | 8. Finishes, Joinery & Fit-out | Built-in wardrobes obstruct vents | Joinery ↔ HVAC | Joinery blocks air. | Res | New build
795 | 8. Finishes, Joinery & Fit-out | Mirror or glass wall cracks from heat | Glass ↔ Heat | Heating sources crack glass. | Res | New build
796 | 8. Finishes, Joinery & Fit-out | Final clean reveals scratches | Finishes ↔ Trades | Protection is needed for finishes. | All | New build
797 | 8. Finishes, Joinery & Fit-out | Defect list longer than expected at practical completion | Quality ↔ Programme | Defects delay handover. | All | All
798 | 8. Finishes, Joinery & Fit-out | Skirting gap at uneven floors | Skirtings ↔ Floors | Uneven floors leave gaps. | Res | New build/Refurb
799 | 8. Finishes, Joinery & Fit-out | Mirror glue fails on damp walls | Mirrors ↔ Moisture | Adhesive needs dry backing. | Res | New build
800 | 8. Finishes, Joinery & Fit-out | Laminate floor buckles with no expansion gap | Flooring ↔ Movement | Floating floors need perimeter gaps. | Res | New build
801 | 9. Site, Logistics & Temporary Works | Crane position conflicts with the permanent structure | Temporary works ↔ Structure | The temporary crane sets the build sequence of the permanent building. | Com | New build
802 | 9. Site, Logistics & Temporary Works | Wind shuts the crane down | Crane ↔ Programme | Lifting capacity governs structural pace. | Com | New build
803 | 9. Site, Logistics & Temporary Works | Scaffold overloaded with materials | Scaffold ↔ Structure | Temporary access structures have limited capacity. | All | All
804 | 9. Site, Logistics & Temporary Works | Road closure blocks deliveries | Site logistics ↔ Construction sequence | Materials must arrive when the sequence needs them. | Com | New build
805 | 9. Site, Logistics & Temporary Works | Council changes driveway levels | Civil ↔ Basement ramp | The ramp slope depends on the street level. | Res/Com | New build
806 | 9. Site, Logistics & Temporary Works | Stormwater easement discovered | Property/civil ↔ Building footprint | Legal and underground constraints limit where structure can go. | All | New build/Extension
807 | 9. Site, Logistics & Temporary Works | Archaeological find | Heritage ↔ Excavation | Heritage law pauses ground disturbance. | Com | New build
808 | 9. Site, Logistics & Temporary Works | Overhead power lines near the crane | Electrical network ↔ Lifting | Crane reach and live conductors must stay apart. | All | All
809 | 9. Site, Logistics & Temporary Works | Flood event during construction | Site drainage ↔ Works in progress | Unfinished drainage cannot protect partial work. | All | New build
810 | 9. Site, Logistics & Temporary Works | Retaining wall drainage fails | Retaining wall ↔ Drainage | Walls are designed on the assumption that water is relieved. | Res/Com | All
811 | 9. Site, Logistics & Temporary Works | Heavy trucks break the pavement subgrade | Civil pavement ↔ Construction traffic | Pavements are designed for service loads not site loads. | Ind/Com | New build
812 | 9. Site, Logistics & Temporary Works | Tower crane swings over a neighbour's property | Crane ↔ Adjoining owner | Overswing needs neighbour permission. | Com | New build
813 | 9. Site, Logistics & Temporary Works | Crane foundation designed for the wrong ground | Crane base ↔ Ground | Crane base loads are high. | Com | New build
814 | 9. Site, Logistics & Temporary Works | Crane erected in a gap between buildings fails the lift study | Crane ↔ Site constraints | Tight sites restrict plant. | Com | New build
815 | 9. Site, Logistics & Temporary Works | Hoist location forces a floor opening | Hoist ↔ Slab edge | Hoists need slab openings and ties. | Com | New build
816 | 9. Site, Logistics & Temporary Works | Hoist ties damage the façade | Hoist ↔ Façade | Tie positions affect the finish. | Com | New build
817 | 9. Site, Logistics & Temporary Works | Material storage overloads a slab | Site storage ↔ Slab | Stacked materials exceed live load. | Com/Res | New build
818 | 9. Site, Logistics & Temporary Works | Edge protection blown off by wind | Edge protection ↔ Wind | Barriers need design for wind. | Com | New build
819 | 9. Site, Logistics & Temporary Works | Falling object hits a neighbouring property | Site safety ↔ Neighbours | Catch fans and hoardings protect others. | Com | New build
820 | 9. Site, Logistics & Temporary Works | Hoarding permit delays start | Hoarding ↔ Council | Street works need approval. | Com | New build
821 | 9. Site, Logistics & Temporary Works | Site access via a narrow street limits truck sizes | Logistics ↔ Streets | Truck sizes affect delivery and cost. | Res/Com | New build/Extension
822 | 9. Site, Logistics & Temporary Works | Concrete pump setup blocks the street | Concrete pour ↔ Traffic | Pumping needs road closures. | Com | New build
823 | 9. Site, Logistics & Temporary Works | Work hours restrictions limit pours | Pours ↔ Noise rules | Large pours require extended hours. | Com | New build
824 | 9. Site, Logistics & Temporary Works | Neighbour complaints cause a stop-work order | Site ↔ Neighbours | Regulators respond to complaints. | Res/Com | All
825 | 9. Site, Logistics & Temporary Works | Dust from demolition blows onto adjoining buildings | Demolition ↔ Neighbours | Dust control is mandatory. | All | Refurb/Upgrade
826 | 9. Site, Logistics & Temporary Works | Noise from jackhammering disturbs hospital | Demolition ↔ Sensitive neighbours | Limits apply near sensitive uses. | Com | Refurb/Upgrade
827 | 9. Site, Logistics & Temporary Works | Vibration from demolition cracks an adjoining wall | Demolition ↔ Adjoining buildings | Vibration travels through ground. | Res/Com | New build
828 | 9. Site, Logistics & Temporary Works | Temporary power supply insufficient | Site power ↔ Plant | Cranes and hoists need three phase. | Com | New build
829 | 9. Site, Logistics & Temporary Works | Temporary water supply cut | Site water ↔ Concrete works | Water is needed for concrete and dust control. | Com | New build
830 | 9. Site, Logistics & Temporary Works | Site toilets blocked by authorities | Site amenity ↔ Sewer | Site amenities need sewer or pump out. | All | New build
831 | 9. Site, Logistics & Temporary Works | Site office located on future excavation | Site establishment ↔ Staging | Offices must move as works progress. | Com | New build
832 | 9. Site, Logistics & Temporary Works | Delivery vehicle damages underground services | Site traffic ↔ Buried services | Traffic loads crush shallow services. | All | All
833 | 9. Site, Logistics & Temporary Works | Heavy rainfall delays the roof completion | Weather ↔ Programme | Roof must be weather-tight before internal trades. | All | New build
834 | 9. Site, Logistics & Temporary Works | Heatwave stops outdoor work | Weather ↔ Labour | Heat limits are mandatory. | All | All
835 | 9. Site, Logistics & Temporary Works | Strong winds stop façade install | Weather ↔ Façade | Wind limits glazing install. | Com | New build
836 | 9. Site, Logistics & Temporary Works | Frost delays brickwork | Weather ↔ Masonry | Frost damages fresh mortar. | Res | New build
837 | 9. Site, Logistics & Temporary Works | Snow load causes roof damage during construction | Weather ↔ Roof structure | Unfinished roofs lack design capacity. | Ind | New build
838 | 9. Site, Logistics & Temporary Works | Cyclone preparation halts site | Weather ↔ Site security | Sites must be secured before storms. | All | All
839 | 9. Site, Logistics & Temporary Works | Bushfire smoke stops works | Environment ↔ Workers | Air quality limits outdoor work. | All | All
840 | 9. Site, Logistics & Temporary Works | Lightning stops crane operations | Weather ↔ Cranes | Lightning forces shutdowns. | Com | New build
841 | 9. Site, Logistics & Temporary Works | Flooded basement from a storm drains into a lift pit | Site water ↔ Building | Unfinished buildings are vulnerable. | Com/Res | New build
842 | 9. Site, Logistics & Temporary Works | Stormwater pit not complete before heavy rain | Stormwater ↔ Site | Unconnected pits flood. | All | New build
843 | 9. Site, Logistics & Temporary Works | Sediment control fails and the council fines | Site erosion ↔ Regulation | Fines apply for polluted water. | All | New build
844 | 9. Site, Logistics & Temporary Works | Native vegetation found on site | Ecology ↔ Development | Protected species affect the footprint. | All | New build
845 | 9. Site, Logistics & Temporary Works | Endangered species halts clearing | Ecology ↔ Programme | Surveys may be required. | Res/Ind | New build
846 | 9. Site, Logistics & Temporary Works | Tree protection zones restrict machine access | Trees ↔ Plant | Roots limit excavation near trees. | Res/Com | New build/Extension
847 | 9. Site, Logistics & Temporary Works | Neighbour's tree overhangs the crane path | Trees ↔ Cranes | Trees limit crane swing. | Res | New build
848 | 9. Site, Logistics & Temporary Works | Contaminated groundwater plume from a neighbour | Neighbour ↔ Site environment | Off-site contamination affects site works. | Com/Ind | New build
849 | 9. Site, Logistics & Temporary Works | Unexploded ordnance suspected on site | Ground ↔ Safety | Surveys needed before digging. | Com/Ind | New build
850 | 9. Site, Logistics & Temporary Works | Heritage overlay discovered late | Planning ↔ Design | Overlays restrict demolition and alterations. | Res/Com | New build/Refurb
851 | 9. Site, Logistics & Temporary Works | Aboriginal cultural heritage found | Cultural heritage ↔ Excavation | Works must stop and be assessed. | All | New build
852 | 9. Site, Logistics & Temporary Works | Easement for a power line prevents building | Utilities ↔ Footprint | Easements restrict building. | Res/Com | New build
853 | 9. Site, Logistics & Temporary Works | Road widening requires land dedication | Planning ↔ Site boundary | Council may take frontage. | Com | New build
854 | 9. Site, Logistics & Temporary Works | Footpath levels dictate entry level | Civil ↔ Entry design | Entry must meet footpath. | Com/Res | New build
855 | 9. Site, Logistics & Temporary Works | Driveway crossing approval delayed | Civil ↔ Council | Crossings need approval. | Res/Com | New build
856 | 9. Site, Logistics & Temporary Works | Street trees conflict with driveway | Landscape ↔ Access | Trees may not be removed. | Res/Com | New build
857 | 9. Site, Logistics & Temporary Works | Services authority requires relocating a pole | Utilities ↔ Frontage | Pole moves are costly and slow. | Res/Com | New build
858 | 9. Site, Logistics & Temporary Works | Telecom pit in the driveway | Utilities ↔ Access | Pits restrict crossings. | Res | New build
859 | 9. Site, Logistics & Temporary Works | Stormwater discharge point inaccessible | Drainage ↔ Council network | Connection must reach the authority's drain. | Res/Com | New build
860 | 9. Site, Logistics & Temporary Works | Fence line dispute | Boundary ↔ Neighbour | Boundaries must be agreed. | Res | New build/Extension
861 | 9. Site, Logistics & Temporary Works | Retaining wall at the boundary needs a neighbour's consent | Retaining wall ↔ Neighbour | Walls near boundaries need agreement. | Res | New build
862 | 9. Site, Logistics & Temporary Works | Excavation near boundaries needs dilapidation survey | Excavation ↔ Neighbours | Pre-existing conditions need to be recorded. | Com | New build
863 | 9. Site, Logistics & Temporary Works | Dilapidation survey disputed | Neighbour ↔ Building condition | Claims depend on the baseline record. | Com | New build
864 | 9. Site, Logistics & Temporary Works | Property damage claim from vibration | Works ↔ Neighbour | Vibration claims need monitoring data. | Com | New build
865 | 9. Site, Logistics & Temporary Works | Landscape irrigation damaged by services trenching | Landscape ↔ Services | Trenching cuts irrigation lines. | Res/Com | New build
866 | 9. Site, Logistics & Temporary Works | Landscape soil depth insufficient over slabs | Landscape ↔ Structure | Podium planting needs soil depth. | Com/Res | New build
867 | 9. Site, Logistics & Temporary Works | Podium slab drainage blocked by soil | Landscape ↔ Drainage | Drainage layers prevent waterlogging. | Com/Res | New build
868 | 9. Site, Logistics & Temporary Works | Tree planted over services | Landscape ↔ Services | Roots damage services. | Com | New build
869 | 9. Site, Logistics & Temporary Works | Trees fail due to poor soil | Landscape ↔ Soil | Soil quality affects survival. | Res/Com | New build
870 | 9. Site, Logistics & Temporary Works | Fence installed on the wrong line | Fencing ↔ Survey | Survey errors cause disputes. | Res | New build
871 | 9. Site, Logistics & Temporary Works | Paving falls toward the building | Paving ↔ Drainage | Falls must go away from walls. | Res/Com | New build
872 | 9. Site, Logistics & Temporary Works | Concrete paving cracks due to roots | Paving ↔ Trees | Roots lift paving. | Res/Com | All
873 | 9. Site, Logistics & Temporary Works | Pavement kerb levels mismatch with the building | Pavement ↔ Building | Levels must meet at entries. | Com | New build
874 | 9. Site, Logistics & Temporary Works | Bollards cannot be installed over services | Bollards ↔ Services | Services limit footings. | Com | New build
875 | 9. Site, Logistics & Temporary Works | Car park line marking misaligned with the structure | Car park ↔ Columns | Bays must avoid columns. | Com | New build
876 | 9. Site, Logistics & Temporary Works | Car park surface water ponding | Pavement ↔ Falls | Poor falls cause ponding. | Com | New build
877 | 9. Site, Logistics & Temporary Works | Truck turning path fails | Site layout ↔ Vehicle movements | Swept paths decide layout. | Ind | New build
878 | 9. Site, Logistics & Temporary Works | Heavy vehicle loads crack pavements | Pavement ↔ Traffic | Industrial pavements need thick design. | Ind | New build
879 | 9. Site, Logistics & Temporary Works | Hardstand falls inadequate | Hardstand ↔ Drainage | Drainage needs consistent falls. | Ind | New build
880 | 9. Site, Logistics & Temporary Works | Rail siding level conflicts with building floor | Rail ↔ Industrial building | Floor level must match rail. | Ind | New build
881 | 9. Site, Logistics & Temporary Works | Weighbridge pit floods | Weighbridge ↔ Drainage | Pits need drainage. | Ind | New build
882 | 9. Site, Logistics & Temporary Works | Stockpile settles the slab | Stockpiles ↔ Slab | Heavy stockpiles load slabs. | Ind | All
883 | 9. Site, Logistics & Temporary Works | Temporary fencing blown over | Site fencing ↔ Wind | Panels need ballast. | All | New build
884 | 9. Site, Logistics & Temporary Works | Site security theft of copper | Security ↔ Services | Theft delays electrical work. | All | New build
885 | 9. Site, Logistics & Temporary Works | Vandalism of the unfinished building | Security ↔ Finishes | Unfinished sites are vulnerable. | Res/Com | New build
886 | 9. Site, Logistics & Temporary Works | Fire in a site shed | Site safety ↔ Fire | Site fire safety is mandatory. | All | All
887 | 9. Site, Logistics & Temporary Works | Workers' safety incident halts the project | Safety ↔ Programme | Regulators can shut sites. | All | All
888 | 9. Site, Logistics & Temporary Works | Silica dust rules restrict cutting | Cutting ↔ Health rules | Engineered stone and concrete need controls. | All | All
889 | 9. Site, Logistics & Temporary Works | Asbestos in an adjoining wall | Neighbour ↔ Hazmat | Neighbour works expose hazards. | Res | Extension
890 | 9. Site, Logistics & Temporary Works | Labour shortage delays framing | Labour ↔ Programme | Trade availability drives programme. | Res | New build
891 | 9. Site, Logistics & Temporary Works | Trade no-shows cause sequence breaks | Trades ↔ Programme | Missing trades delay the next trade. | All | All
892 | 9. Site, Logistics & Temporary Works | Key trade goes insolvent | Contract ↔ Programme | Replacement trades take time. | All | All
893 | 9. Site, Logistics & Temporary Works | Subcontractor defects emerge after payment | Quality ↔ Contract | Retention manages risk. | All | All
894 | 9. Site, Logistics & Temporary Works | Material price spike | Procurement ↔ Budget | Escalation threatens cost. | All | All
895 | 9. Site, Logistics & Temporary Works | Shipping delay of imported cladding | Procurement ↔ Façade | International supply is slow. | Com | New build
896 | 9. Site, Logistics & Temporary Works | Customs rejection of a product | Imports ↔ Compliance | Non-conforming products can be held. | Com | New build
897 | 9. Site, Logistics & Temporary Works | Excavator strikes a gas main | Excavation ↔ Gas network | Gas mains are a life safety risk. | All | All
898 | 9. Site, Logistics & Temporary Works | Temporary works design not provided for propping | Temporary works ↔ Structure | Temporary design must be independent. | Com | New build
899 | 9. Site, Logistics & Temporary Works | Delivery crane cannot reach due to overhead lines | Delivery ↔ Overhead lines | Lines restrict crane reach. | Res | New build
900 | 9. Site, Logistics & Temporary Works | Council inspection delays slab pour | Council ↔ Concrete programme | Pour waits on inspection. | Res | New build
901 | 10. Regulation, Procurement, Existing Buildings & Handover | Authority requires an NCC design change | Architecture ↔ Regulation | Design must comply and compliance changes design. | All | All
902 | 10. Regulation, Procurement, Existing Buildings & Handover | Certifier rejects an inspection | Quality ↔ Programme | The next trade cannot start until the previous work is approved. | All | All
903 | 10. Regulation, Procurement, Existing Buildings & Handover | Material shortage | Procurement ↔ Programme | Supply drives the construction sequence. | All | All
904 | 10. Regulation, Procurement, Existing Buildings & Handover | Substituted sealant will not bond | Sealants ↔ Façade substrates | Compatibility decides whether joints seal. | Com | New build
905 | 10. Regulation, Procurement, Existing Buildings & Handover | Latent site condition triggers a claim | Contract ↔ Ground/structure | Risk allocation determines who pays for unknowns. | All | All
906 | 10. Regulation, Procurement, Existing Buildings & Handover | Trades stacking in the same area | Multiple trades ↔ Sequence | Work must be ordered so each trade's output is not damaged. | All | All
907 | 10. Regulation, Procurement, Existing Buildings & Handover | Asbestos found in the existing building | Demolition ↔ Hazmat | Removal must be safe before any new work begins. | All | Refurb/Upgrade
908 | 10. Regulation, Procurement, Existing Buildings & Handover | Commissioning reveals unintegrated systems | All services ↔ Controls | Systems designed separately have to work as one. | Com | New build
909 | 10. Regulation, Procurement, Existing Buildings & Handover | As-built differs from the drawings | Documentation ↔ Operation | Maintenance depends on records matching reality. | All | All
910 | 10. Regulation, Procurement, Existing Buildings & Handover | Defects emerge in the defects period | Completed work ↔ Occupancy | Real use stresses systems in ways testing does not. | All | All
911 | 10. Regulation, Procurement, Existing Buildings & Handover | Design not coordinated before tender | Design disciplines ↔ Pricing | Clashes found late cost more. | Com | New build
912 | 10. Regulation, Procurement, Existing Buildings & Handover | Drawings issued with unresolved clashes | Design ↔ Construction | Contractors build what is drawn. | All | All
913 | 10. Regulation, Procurement, Existing Buildings & Handover | Late consultant design changes | Design ↔ Procurement | Changes ripple to ordered items. | Com | New build
914 | 10. Regulation, Procurement, Existing Buildings & Handover | Design team does not coordinate on a 3D model | Design ↔ Coordination | Model clashes appear on site otherwise. | Com | New build
915 | 10. Regulation, Procurement, Existing Buildings & Handover | Architect specifies a discontinued product | Spec ↔ Supply | Product availability affects design. | All | All
916 | 10. Regulation, Procurement, Existing Buildings & Handover | Specification conflicts with drawings | Spec ↔ Drawings | Order of precedence decides. | All | All
917 | 10. Regulation, Procurement, Existing Buildings & Handover | RFI response takes weeks | Design ↔ Site | Delayed answers stop work. | All | All
918 | 10. Regulation, Procurement, Existing Buildings & Handover | Shop drawing approval delays | Procurement ↔ Fabrication | Fabrication waits on approval. | Com | New build
919 | 10. Regulation, Procurement, Existing Buildings & Handover | Sample approval rejected | Finishes ↔ Procurement | Samples confirm the quality. | Com | New build
920 | 10. Regulation, Procurement, Existing Buildings & Handover | Client changes the brief mid-construction | Brief ↔ Design | Changes affect all trades. | All | All
921 | 10. Regulation, Procurement, Existing Buildings & Handover | Client-supplied items arrive late | Client supply ↔ Programme | Items outside contract risk delay. | Res/Com | All
922 | 10. Regulation, Procurement, Existing Buildings & Handover | Client variation approvals slow | Contract ↔ Cash flow | Delays impact progress. | All | All
923 | 10. Regulation, Procurement, Existing Buildings & Handover | Provisional sum allowances too low | Budget ↔ Scope | Allowances underpriced. | Res/Com | All
924 | 10. Regulation, Procurement, Existing Buildings & Handover | Cost plan does not allow for services complexity | Budget ↔ Services | Services costs grow with detail. | Com | New build
925 | 10. Regulation, Procurement, Existing Buildings & Handover | Tender price exceeds budget | Procurement ↔ Design | Value engineering is needed. | All | New build
926 | 10. Regulation, Procurement, Existing Buildings & Handover | Value engineering removes a critical item | VE ↔ Performance | Savings can affect function. | All | All
927 | 10. Regulation, Procurement, Existing Buildings & Handover | Value engineering changes a material and fails compliance | VE ↔ Regulation | Changes must be reassessed. | All | All
928 | 10. Regulation, Procurement, Existing Buildings & Handover | Procurement strategy mismatched to risk | Procurement ↔ Risk | Contract form allocates risk. | All | All
929 | 10. Regulation, Procurement, Existing Buildings & Handover | Novation of consultants causes design gaps | Contract ↔ Design | Design responsibility shifts. | Com | New build
930 | 10. Regulation, Procurement, Existing Buildings & Handover | Design and construct contractor changes design intent | Contract ↔ Design | D&C allows changes. | Com | New build
931 | 10. Regulation, Procurement, Existing Buildings & Handover | Builder does not read the contract special conditions | Contract ↔ Execution | Special conditions allocate risk. | All | All
932 | 10. Regulation, Procurement, Existing Buildings & Handover | Time bar notice missed | Contract ↔ Claims | Notices must be timely. | All | All
933 | 10. Regulation, Procurement, Existing Buildings & Handover | Extension of time disputed | Contract ↔ Programme | Delay events need evidence. | All | All
934 | 10. Regulation, Procurement, Existing Buildings & Handover | Liquidated damages applied | Contract ↔ Delay | Delay carries cost. | All | All
935 | 10. Regulation, Procurement, Existing Buildings & Handover | Security of payment claim lodged | Contract ↔ Payments | Rapid adjudication affects cash. | All | All
936 | 10. Regulation, Procurement, Existing Buildings & Handover | Retention release dispute | Contract ↔ Defects | Retention covers defects. | All | All
937 | 10. Regulation, Procurement, Existing Buildings & Handover | Contractor insolvency during build | Contract ↔ Completion | Replacement contractor needed. | Res/Com | All
938 | 10. Regulation, Procurement, Existing Buildings & Handover | Developer finance withdrawn | Funding ↔ Programme | Funding is the lifeblood of the project. | Res/Com | New build
939 | 10. Regulation, Procurement, Existing Buildings & Handover | Presales not met and finance falls over | Finance ↔ Residential | Lenders require presales. | Res | New build
940 | 10. Regulation, Procurement, Existing Buildings & Handover | Interest rate rises affect feasibility | Finance ↔ Project viability | Costs of funds change viability. | Res/Com | New build
941 | 10. Regulation, Procurement, Existing Buildings & Handover | Strata plan registration delayed | Legal ↔ Settlement | Settlements depend on titles. | Res | New build
942 | 10. Regulation, Procurement, Existing Buildings & Handover | Sale settlement delayed by an occupancy certificate | Approvals ↔ Sales | Settlement requires OC. | Res | New build
943 | 10. Regulation, Procurement, Existing Buildings & Handover | Owners corporation defect claims | Quality ↔ Strata | Strata claims follow completion. | Res | New build
944 | 10. Regulation, Procurement, Existing Buildings & Handover | Building defects insurance triggered | Quality ↔ Insurance | Insurers require documentation. | Res | New build
945 | 10. Regulation, Procurement, Existing Buildings & Handover | Warranty claims on waterproofing | Waterproofing ↔ Warranty | Warranties depend on correct installation. | Res | New build
946 | 10. Regulation, Procurement, Existing Buildings & Handover | Product recall | Materials ↔ Safety | Recalled products must be replaced. | All | All
947 | 10. Regulation, Procurement, Existing Buildings & Handover | Non-conforming building product found | Materials ↔ Compliance | Product bans require removal. | All | All
948 | 10. Regulation, Procurement, Existing Buildings & Handover | Imported product lacks certification | Procurement ↔ Compliance | Certificates decide acceptance. | All | All
949 | 10. Regulation, Procurement, Existing Buildings & Handover | Cladding audit requires rectification | Cladding ↔ Regulation | Audits can force remediation. | Res | Refurb/Upgrade
950 | 10. Regulation, Procurement, Existing Buildings & Handover | Combustible cladding remediation | Cladding ↔ Fire safety | Replacement needs access and approvals. | Res/Com | Refurb/Upgrade
951 | 10. Regulation, Procurement, Existing Buildings & Handover | Remediation reveals structural damage | Cladding remediation ↔ Structure | Removing cladding exposes defects. | Res | Refurb/Upgrade
952 | 10. Regulation, Procurement, Existing Buildings & Handover | Building services upgrade triggers whole-of-building compliance | Upgrade ↔ Regulation | Alterations can trigger upgrades. | Com | Refurb/Upgrade
953 | 10. Regulation, Procurement, Existing Buildings & Handover | Change of use requires upgrades to fire, access and energy | Use change ↔ Regulation | Use class sets requirements. | Com/Res | Refurb/Upgrade
954 | 10. Regulation, Procurement, Existing Buildings & Handover | Heritage listing blocks alterations | Heritage ↔ Alterations | Significant fabric must stay. | Res/Com | Refurb/Upgrade
955 | 10. Regulation, Procurement, Existing Buildings & Handover | Heritage consultant requires original materials | Heritage ↔ Procurement | Authentic materials are hard to source. | Res/Com | Refurb/Upgrade
956 | 10. Regulation, Procurement, Existing Buildings & Handover | Specialist trade shortage for heritage works | Heritage ↔ Labour | Heritage trades are scarce. | Res/Com | Refurb/Upgrade
957 | 10. Regulation, Procurement, Existing Buildings & Handover | Occupied building refurb limits working hours | Refurb ↔ Occupants | Occupants restrict noisy works. | Com | Refurb/Upgrade
958 | 10. Regulation, Procurement, Existing Buildings & Handover | Tenant complaints about noise or dust | Refurb ↔ Occupants | Operating buildings tolerate little disruption. | Com | Refurb/Upgrade
959 | 10. Regulation, Procurement, Existing Buildings & Handover | Hospital refurb requires infection control barriers | Refurb ↔ Clinical | Dust control protects patients. | Com | Refurb/Upgrade
960 | 10. Regulation, Procurement, Existing Buildings & Handover | School works restricted to holidays | Refurb ↔ Operations | Occupancy windows limit works. | Com | Refurb/Upgrade
961 | 10. Regulation, Procurement, Existing Buildings & Handover | Retail refurb must finish before trading peak | Refurb ↔ Retail calendar | Fixed deadlines drive programme. | Com | Refurb/Upgrade
962 | 10. Regulation, Procurement, Existing Buildings & Handover | Staged handover needs separate services isolation | Staging ↔ Services | Partial occupation needs safe services. | Com | Refurb/Upgrade
963 | 10. Regulation, Procurement, Existing Buildings & Handover | Existing building services not as documented | Documentation ↔ Reality | Unknown conditions drive variations. | All | Refurb/Upgrade
964 | 10. Regulation, Procurement, Existing Buildings & Handover | Hidden conditions behind linings | Existing building ↔ Unknown | Opening up reveals defects. | Res | Refurb/Upgrade
965 | 10. Regulation, Procurement, Existing Buildings & Handover | Termite damage found after stripping | Timber ↔ Termites | Hidden damage requires repair. | Res | Refurb/Upgrade
966 | 10. Regulation, Procurement, Existing Buildings & Handover | Old building has no fire compartments | Existing building ↔ Fire code | Upgrade is required for use. | Com/Res | Refurb/Upgrade
967 | 10. Regulation, Procurement, Existing Buildings & Handover | Existing slab levels vary requiring bigger screed | Existing slab ↔ New floors | Old slabs are rarely flat. | Com | Refurb/Upgrade
968 | 10. Regulation, Procurement, Existing Buildings & Handover | New work cannot match existing profile | New ↔ Existing | Old profiles differ from current products. | Res | Extension/Refurb
969 | 10. Regulation, Procurement, Existing Buildings & Handover | Existing ceiling heights restrict new services | Existing ↔ New services | Old buildings have low voids. | Com | Refurb/Upgrade
970 | 10. Regulation, Procurement, Existing Buildings & Handover | Floor-to-floor height inadequate for new HVAC | Existing structure ↔ New HVAC | Old height limits modern systems. | Com | Refurb/Upgrade
971 | 10. Regulation, Procurement, Existing Buildings & Handover | Extension approvals take longer than expected | Planning ↔ Extension | Councils are slow. | Res | Extension
972 | 10. Regulation, Procurement, Existing Buildings & Handover | Neighbour objections to an extension | Planning ↔ Neighbours | Objections delay approvals. | Res | Extension
973 | 10. Regulation, Procurement, Existing Buildings & Handover | Overshadowing rules limit an extension height | Planning ↔ Extension | Shadow diagrams are required. | Res | Extension
974 | 10. Regulation, Procurement, Existing Buildings & Handover | Floor area ratio limit reached | Planning ↔ Extension | Planning controls cap area. | Res | Extension
975 | 10. Regulation, Procurement, Existing Buildings & Handover | Extension requires upgrading of the existing house | Existing ↔ New compliance | Alterations trigger upgrades. | Res | Extension
976 | 10. Regulation, Procurement, Existing Buildings & Handover | Extension finishes do not match existing colours | New ↔ Old finishes | Old finishes weather and age. | Res | Extension
977 | 10. Regulation, Procurement, Existing Buildings & Handover | Existing roof drainage cannot handle extension flows | Drainage ↔ Extension | Capacity may be limited. | Res | Extension
978 | 10. Regulation, Procurement, Existing Buildings & Handover | Services relocation for an extension | Existing services ↔ New footprint | Services run where the new building wants to go. | Res | Extension
979 | 10. Regulation, Procurement, Existing Buildings & Handover | Commissioning programme squeezed | Commissioning ↔ Handover | Testing needs time. | Com | New build
980 | 10. Regulation, Procurement, Existing Buildings & Handover | Commissioning begins before systems complete | Commissioning ↔ Installation | Incomplete systems cannot be tested. | Com | New build
981 | 10. Regulation, Procurement, Existing Buildings & Handover | Seasonal testing of HVAC not possible before handover | Commissioning ↔ Weather | Systems need hot and cold tests. | Com | New build
982 | 10. Regulation, Procurement, Existing Buildings & Handover | Training of building operators skipped | Handover ↔ Operations | Operators need to understand systems. | Com | New build
983 | 10. Regulation, Procurement, Existing Buildings & Handover | O&M manuals incomplete | Handover ↔ Maintenance | Manuals decide life-cycle performance. | Com | New build
984 | 10. Regulation, Procurement, Existing Buildings & Handover | Warranty documents missing | Handover ↔ Owner | Warranties require registration. | All | All
985 | 10. Regulation, Procurement, Existing Buildings & Handover | Spare parts and keys not handed over | Handover ↔ Operation | Handover items are contract requirements. | Com | New build
986 | 10. Regulation, Procurement, Existing Buildings & Handover | Practical completion disputed | Contract ↔ Completion | PC definitions vary. | All | All
987 | 10. Regulation, Procurement, Existing Buildings & Handover | Defects liability period work is disruptive | Defects ↔ Occupants | Defect fixes impact occupants. | Com | All
988 | 10. Regulation, Procurement, Existing Buildings & Handover | Latent defects appear after the defects period | Quality ↔ Long-term performance | Latent defects emerge after years. | All | All
989 | 10. Regulation, Procurement, Existing Buildings & Handover | Building performance below the NABERS or Green Star target | Design ↔ Operation | Performance depends on operation. | Com | New build
990 | 10. Regulation, Procurement, Existing Buildings & Handover | Post-occupancy complaints about comfort | Design ↔ Occupants | Occupant feedback reveals gaps. | Com | New build
991 | 10. Regulation, Procurement, Existing Buildings & Handover | Development consent lapses before start | Planning ↔ Programme | Consents expire. | Res/Com | New build
992 | 10. Regulation, Procurement, Existing Buildings & Handover | Modification application needed for minor changes | Approvals ↔ Design | Changes to approved plans need approval. | Res/Com | New build
993 | 10. Regulation, Procurement, Existing Buildings & Handover | Conditions of consent require third party works | Consent ↔ Off-site works | Off-site works rely on others. | Com | New build
994 | 10. Regulation, Procurement, Existing Buildings & Handover | Developer contributions are re-assessed | Planning ↔ Budget | Contribution levies change. | Res/Com | New build
995 | 10. Regulation, Procurement, Existing Buildings & Handover | Subdivision certificate delayed | Approvals ↔ Settlement | Titles require approvals. | Res | New build
996 | 10. Regulation, Procurement, Existing Buildings & Handover | Utility headworks charges increase | Utilities ↔ Budget | Charges vary by authority. | Res/Com | New build
997 | 10. Regulation, Procurement, Existing Buildings & Handover | Fixed-price contract on unresolved design | Contract ↔ Design | Incomplete design drives variations. | All | All
998 | 10. Regulation, Procurement, Existing Buildings & Handover | Dispute escalates to adjudication | Contract ↔ Programme | Disputes slow work. | All | All
999 | 10. Regulation, Procurement, Existing Buildings & Handover | Insurance does not cover a weather event | Insurance ↔ Risk | Policy exclusions create exposure. | All | All
1000 | 10. Regulation, Procurement, Existing Buildings & Handover | Site possession delayed by tenant holdover | Tenancy ↔ Programme | Refurbs rely on vacant possession. | Com | Refurb/Upgrade

## Summary
Theme | Count
1. Ground, Earthworks & Foundations | 100
2. Structure & Structural Frame | 100
3. Building Envelope & Waterproofing | 100
4. Fire, Life Safety & Compliance | 100
5. Hydraulics, Drainage & Gas | 100
6. Mechanical, Vertical Transport & Acoustics | 100
7. Electrical, Communications & Controls | 100
8. Finishes, Joinery & Fit-out | 100
9. Site, Logistics & Temporary Works | 100
10. Regulation, Procurement, Existing Buildings & Handover | 100
Total | 1000
Key: Building category = Res (residential), Com (commercial), Ind (industrial), All.
Key: Project type = New build, Extension, Refurb/Upgrade, All.